## NFS Dashboard
Site | Discipline | Dept | Position No | JOB TITLE per manning | BarChart Mob Date | BarChart Demob Date | Entity | Pay Cat | Candidate'a name | Current Mob Step
NFS - SITE | Management | PCCSU | PCCSU-00-A-01-01b | Project Commissioning Manager | 2025-10-05 | 2028-10-15 | EXP | DIR | Bernard CAUSSANEL | Under mobilization
NFS - SITE | Management | PCCSU | PCCSU-00-A-02-01b | Deputy Commissioning Manager Process Train 12 &13 | 2025-01-01 | 2028-10-15 | EXP | A | Anis BEN MILED - TEN POC | ON SITE
NFS - SITE | Management | PCCSU | PCCSU-00-A-02-02 | Deputy Commissioning Manager U&O | 2025-07-26 | 2028-06-30 | EXP | A | Fiorenzo CAPUZZIMATI - TEN ROC | Under mobilization
NFS - SITE | Management | PCCSU | PCCSU-00-A-03-01 | Lead Start-up Engineer (Process) | 2027-05-01 | 2028-10-15 | EXP | A
NFS - SITE | Management | PCCSU | PCCSU-00-A-03-02 | Lead Start-up Engineer (U&O) | 2026-05-01 | 2028-07-15 | EXP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-A-04-01 | O&M Manager | 2026-03-01 | 2028-09-30 | EXP | B
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-A-04-09 | Commissioning Superintendent (Building) | 2025-10-01 | 2028-04-15 | EXP | B
NFS - SITE | Management | PCCSU | PCCSU-00-B-01-01 | Commissioning Lead Engineer | 2027-02-15 | 2028-04-15 | DHP | B
NFS - SITE | Management | PCCSU | PCCSU-00-B-02-01 | Commissioning Lead Interface Engineer | 2025-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-02-02b | Tr-12 Commissioning Lead Engineer (Process_Cold) | 2026-02-01 | 2028-10-15 | EXP | B2 | Youseef ZGAR - TEN POC | 2026 NFS shortlist
NFS - SITE | Process | PCCSU | PCCSU-00-B-03-01a | Lead Process Engineer U/O | 2025-04-01 | 2025-12-31 | EXP | B | Domenico SPADAFORA - TEN ROC | ON SITE
NFS - SITE | Process | PCCSU | PCCSU-00-B-03-01b | Lead Process Engineer U/O | 2026-01-01 | 2026-03-31 | EXP | B | Potential continuation of Domenico SPADAFORA?
NFS - SITE | Process | PCCSU | PCCSU-00-B-03-02 | Process Engineer LNG Train | 2027-06-01 | 2028-10-15 | EXP | B
NFS - SITE | Support | PCCSU | PCCSU-00-B-04-01 | Commissioning reporting Lead | 2026-06-01 | 2028-09-30 | DHP | B
NFS - SITE | Material | PCCSU | PCCSU-00-B-05-01 | Commissioning Lead Material and support | 2026-03-01 | 2028-10-15 | DHP | C
NFS - SITE | Material | PCCSU | PCCSU-00-B-06-01 | Commissioning Temporaries Coordinator | 2026-09-01 | 2028-04-15 | DHP | B
NFS - SITE | Material | PCCSU | PCCSU-00-B-07-01 | Commissioning Material Cordinator | 2026-03-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-01 | Tr-12 Commissioning Superintendent (Process_Hot) | 2025-01-01 | 2028-10-15 | DHP | A | Manuel CUSTODIO - TPFQ | ON SITE
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-02 | Tr-12 Commissioning Superintendent (Process_Cold) | 2026-03-01 | 2028-10-15 | EXP | B2
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-03 | Tr-13 Commissioning Superintendent (Process Hot) | 2027-08-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-04 | Tr-13 Commissioning Superintendant (Process cold) | 2027-07-01 | 2028-09-30 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-05 | Commissioning Superintendant (SRU) | 2026-10-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-06 | Commissioning Superintendant (Utility and desalination) | 2025-10-01 | 2028-09-30 | EXP | A | Roberto PRATO - TEN ROC | Medical review
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-07 | Commissioning Superintendant (Offsite/Offplot) | 2026-06-01 | 2028-05-30 | EXP | B | Andres ZAMBRANO ANDRAUSS - TEN ROC | 2026 NFS shortlist
NFS - SITE | Process | PCCSU | PCCSU-00-B-08-08 | Commissioning Superintendant (INLET) | 2027-01-01 | 2028-04-15 | EXP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-09-01 | Tr-12/13 Operation Shift Superintendant | 2026-09-01 | 2028-09-30 | DHP | D
NFS - SITE | O&M | PCCSU | PCCSU-00-B-09-02 | Tr-12/13 Operation Shift Superintendant | 2026-09-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-09-03 | Tr-12/13 Operation Shift Superintendant | 2027-01-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-10-01 | Maintenance Superintendant | 2026-03-01 | 2028-09-30 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-02 | Tr-12 Commissioning Lead Engineer (Process_Cold) | 2026-10-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-03 | Tr-12 Commissioning Lead Engineer (Process_Hot) | 2026-11-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-04 | Tr-12 Commissioning Lead Engineer (Process_Hot) | 2026-04-01 | 2028-10-15 | EXP | B | Amine NASSEH - TEN POC | 2026 NFS shortlist
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-05 | Tr-13 Commissioning Lead Engineer (Process_Cold) | 2027-08-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-06 | Tr-13 Commissioning Lead Engineer (Process_Cold) | 2027-09-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-07 | Tr-13 Commissioning Lead Engineer (Process_Hot) | 2027-10-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-08 | Commissioning Lead Engineer (SRU3) | 2026-11-30 | 2028-05-30 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-09 | Commissioning Lead Engineer (CW,Air,N2) | 2026-01-01 | 2028-09-30 | EXP | B | Stefano TOMASSINI - TEN ROC | 2026 NFS shortlist
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-10 | Commissioning Lead Engineer (Steam,...) | 2026-01-01 | 2028-07-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-11 | Commissioning Lead Engineer (Power) | 2026-01-01 | 2028-07-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-12 | Commissioning Lead Engineer (Inlet) | 2026-06-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-13 | Commissioning Lead Engineer (Inlet) | 2026-05-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-14 | Lead Commissioning Engineer (SRU) | 2026-06-01 | 2028-10-15 | EXP | B | Louis FOURCADE - TEN POC | 2026 NFS shortlist
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-15 | Commissioning Lead Engineer (Offsite/Offplot) | 2026-01-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-16 | Commissioning Lead Engineer (Desal/Electro) | 2025-11-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-17 | Commissioning Lead Engineer (Offsite/Offplot) | 2026-03-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-B-11-18 | Commissioning Lead Engineer (Offsite/Offplot) | 2026-04-01 | 2028-05-31 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-12-01 | Operation Superindendant | 2026-06-01 | 2028-09-30 | DHP | B | (Valentin CABULEA) | 2026 NFS shortlist
NFS - SITE | O&M | PCCSU | PCCSU-00-B-13-01 | Tr-12/13 Maintenance Lead Shift Engineer | 2026-05-01 | 2028-06-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-13-02 | Tr-12/13 Maintenance Lead Shift Engineer | 2026-09-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-13-03 | Tr-12/13 Maintenance Lead Shift Engineer | 2026-08-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-14-01 | Panel Operator | 2026-09-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-14-02 | Panel Operator | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-14-03 | Panel Operator | 2026-12-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-15-01 | Field shift Supervisor | 2026-10-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-15-02 | Field shift Supervisor | 2026-09-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-15-03 | Field shift Supervisor | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-15-04 | Field shift Supervisor | 2026-12-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-16-01 | Training Manager | 2026-05-01 | 2028-04-15 | EXP | A
NFS - SITE | O&M | PCCSU | PCCSU-00-B-16-02 | Training Assistant | 2026-06-01 | 2028-09-30 | DHP | D
NFS - SITE | O&M | PCCSU | PCCSU-00-B-17-01 | O&M Training Coordinator #1 | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | O&M | PCCSU | PCCSU-00-B-17-02 | O&M Training Coordinator #2 | 2027-04-01 | 2028-03-31 | DHP | B
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-B-18-01 | Commissioning Engineer OFFSITE | 2026-06-01 | 2028-04-15 | DHP | B
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-B-18-02 | Commissioning Engineer UTILITY | 2026-02-01 | 2028-04-15 | DHP | B
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-B-18-03 | Commissioning Engineer PROCESS | 2026-05-01 | 2028-07-31 | DHP | B
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-B-18-04 | Commissioning Engineer Admin area (PHA-1) (Building) | 2025-10-01 | 2027-08-30 | DHP | B | Magno AQUIATAN - TPFQ | Under mobilization
NFS - SITE | Management | PCCSU | PCCSU-00-C-01-01 | BIC Coordinator (Process) | 2026-04-01 | 2028-06-30 | EXP | C
NFS - SITE | Management | PCCSU | PCCSU-00-C-01-02 | BIC Coordinator (U&O) | 2026-03-01 | 2027-12-31 | DHP | C
NFS - SITE | Material | PCCSU | PCCSU-00-C-02-01 | Commissioning Supporting Supervisor | 2026-08-01 | 2028-03-31 | DHP | C
NFS - SITE | Material | PCCSU | PCCSU-00-C-02-02 | Commissioning Supporting Supervisor | 2027-01-01 | 2028-10-15 | DHP | C
NFS - SITE | Material | PCCSU | PCCSU-00-C-03-01 | Commissioning Material Supervisor | 2026-06-01 | 2028-04-15 | DHP | C
NFS - SITE | Material | PCCSU | PCCSU-00-C-03-02 | Commissioning Material Supervisor | 2027-02-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-01 | Tr-12 Commissioning Lead Supervisor (Process) | 2026-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-02 | Tr-12 Commissioning Lead Supervisor (Process) | 2026-10-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-03 | Tr-12 Commissioning Lead Supervisor (Process) | 2026-10-01 | 2028-10-15 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-04 | Tr-13 Commissioning Lead Supervisor (Process_Hot) | 2027-08-01 | 2028-10-15 | EXP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-05 | Commissioning Lead Supervisor (UOI) | 2025-12-01 | 2028-07-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-06 | Commissioning Lead Supervisor (UOI) | 2026-01-01 | 2028-07-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-07 | Commissioning Lead Supervisor (UOI) | 2027-03-01 | 2028-08-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-08 | Commissioning Lead Supervisor (UOI) | 2026-06-01 | 2028-08-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-04-09 | Commissioning Lead Supervisor (UOI) | 2026-06-01 | 2028-05-31 | DHP | B
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-01 | Tr-12 Commissioning Supervisor (Process) | 2026-11-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-02 | Tr-12 Commissioning Supervisor (Process) | 2026-12-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-03 | Tr-12 Commissioning Supervisor (Process) | 2027-01-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-04 | Tr-12 Commissioning Supervisor (Process) | 2027-01-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-05 | Tr-12 Commissioning Supervisor (Process) | 2027-02-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-06 | Tr-12 Commissioning Supervisor (Process) | 2027-03-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-07 | Tr-12 Commissioning Supervisor (Process) | 2027-03-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-08 | Tr-12 Commissioning Supervisor (Process) | 2027-04-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-09 | Tr-13 Commissioning Supervisor (Process) | 2028-04-15 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-10 | Tr-13 Commissioning Supervisor (Process) | 2028-04-15 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-11 | Tr-13 Commissioning Supervisor (Process) | 2027-05-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-12 | Tr-13 Commissioning Supervisor (Process) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-13 | Tr-13 Commissioning Supervisor (Process) | 2027-07-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-14 | Tr-13 Commissioning Supervisor (Process) | 2027-08-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-15 | Tr-13 Commissioning Supervisor (Process) | 2027-09-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-16 | Tr-13 Commissioning Supervisor (Process) | 2027-09-15 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-17 | Commissioning Supervisor (SRU) | 2026-09-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-18 | Commissioning Supervisor (SRU) | 2026-09-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-19 | Commissioning Supervisor (SRU) | 2027-01-01 | 2028-10-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-20 | Commissioning Supervisor (SRU) | 2027-03-01 | 2028-04-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-21 | Commissioning Supervisor (SRU) | 2026-11-01 | 2028-04-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-22 | Commissioning Supervisor (UOI) | 2026-06-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-23 | Commissioning Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-24 | Commissioning Supervisor (UOI) | 2026-07-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-25 | Commissioning Supervisor (UOI) | 2026-03-01 | 2028-03-31 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-26 | Commissioning Supervisor (UOI) | 2026-09-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-27 | Commissioning Supervisor (UOI) | 2026-09-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-28 | Commissioning Supervisor (UOI) | 2026-10-01 | 2028-09-30 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-29 | Commissioning Supervisor (UOI) | 2026-08-01 | 2028-05-31 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-30 | Commissioning Supervisor (UOI) | 2026-09-01 | 2028-05-31 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-31 | Commissioning Supervisor (UOI) | 2026-09-01 | 2028-05-31 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-32 | Commissioning Supervisor (UOI) | 2026-09-01 | 2028-05-31 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-33 | Commissioning Supervisor (UOI) | 2027-03-01 | 2028-04-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-05-34 | Commissioning Supervisor (UOI) | 2027-03-01 | 2028-04-15 | DHP | C
NFS - SITE | Process | PCCSU | PCCSU-00-C-06-01 | Operation Support Process Engineer | 2026-11-01 | 2028-04-15 | EXP | B1
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-C-07-01 | Building supervisor | 2025-12-01 | 2028-04-15 | DHP | C
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-C-07-02 | Building supervisor | 2026-01-01 | 2028-04-15 | DHP | C
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-C-07-03 | Building supervisor | 2026-02-01 | 2028-04-15 | DHP | C
NFS - SITE | Building / HVAC | PCCSU | PCCSU-00-C-07-04 | Building supervisor | 2026-03-01 | 2028-07-31 | DHP | C
NFS - SITE | Support | PCCSU | PCCSU-00-D-01-01 | Commissioning Group Lead assistant | 2025-10-01 | 2028-10-15 | DHP | D
NFS - SITE | Support | PCCSU | PCCSU-00-D-02-01 | Commissioning Assistant | 2026-09-01 | 2028-06-01 | DHP | D
NFS - SITE | Support | PCCSU | PCCSU-00-E-01-01 | Commissioning Clerk | 2025-10-01 | 2028-10-15 | DHP | E
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-01-01 | I&C Senior Comm.Superintendant | 2026-01-01 | 2028-10-15 | EXP | A | Regis SIMON - TEN POC | 2026 NFS shortlist
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-02-01 | Control system Superintendant | 2026-02-01 | 2028-10-15 | EXP | A
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-03-01 | Instrument Superindentant (Process & SRU) | 2026-03-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-03-02 | Instrument Superintendant (UOI) | 2026-01-01 | 2028-10-15 | EXP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-04-01 | Telecom Superintendent | 2026-07-01 | 2028-10-15 | EXP | A
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-01 | Instrument Lead Engineer (Process Hot) | 2026-05-01 | 2028-10-15 | DHP | A
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-02 | Instrument Lead Engineer (Process cold) | 2026-06-01 | 2028-10-15 | DHP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-03 | Instrument Lead Engineer (Train-13) | 2027-04-01 | 2028-10-15 | EXP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-04 | Instrument Lead Engineer (SRU) | 2026-09-01 | 2028-10-15 | EXP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-05 | Instrument Lead Engineer (Utility) | 2025-09-15 | 2028-10-15 | EXP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-06 | Instrument Lead Engineer (Inlet) | 2026-08-01 | 2028-05-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-05-07 | Instrument Lead Engineer (Offsite/Offplot) | 2026-03-01 | 2028-06-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-01 | Control System Lead Engineer (process Hot) | 2026-03-01 | 2028-10-15 | EXP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-02 | Control System Lead Engineer (Process cold) | 2026-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-03 | Control System Lead Engineer (SRU) | 2026-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-04 | Control System Lead Engineer (Utility) | 2025-10-15 | 2028-10-15 | DHP | B | Shohrat HOJYYEV - GC HUB | Medical review
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-05 | Control System Lead Engineer (SMCB) | 2026-03-01 | 2028-10-15 | DHP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-06 | Control System Lead Engineer (inlet) | 2026-08-01 | 2028-04-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-06-07 | Control System Lead Engineer (Offsite/Offplot) | 2026-05-01 | 2028-06-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-07-01 | Control System Lead Engineer (Train-13) | 2027-06-01 | 2028-10-15 | EXP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-08-01 | Telecom Lead Engineer (UOI) | 2026-04-01 | 2028-09-30 | EXP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-08-02 | Telecom Lead Engineer (Process & SRU) | 2026-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-09-01 | Lab Lead Engineer | 2026-11-01 | 2028-08-31 | EXP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-01 | Control System Engineer (Process) | 2026-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-02 | Control System Engineer (Process) | 2026-12-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-03 | Control System Engineer (Process) | 2027-03-01 | 2028-10-15 | DHP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-04 | Control System Engineer (Process) | 2027-05-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-05 | Control System Engineer (Process) | 2026-12-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-06 | Control System Engineer (Train-13) | 2027-06-15 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-07 | Control System Engineer (Train-13) | 2027-06-30 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-08 | Control System Engineer (SRU) | 2027-03-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-09 | Control System Engineer (UOI) | 2026-11-01 | 2028-05-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-10 | Control System Engineer (UOI) | 2026-07-01 | 2028-09-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-11 | Control System Engineer (UOI) | 2027-04-01 | 2028-09-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-12 | Control System Engineer (UOI) | 2026-04-01 | 2028-09-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-13 | Control System Engineerr (UOI) | 2026-07-01 | 2028-09-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-10-14 | Control System Engineerr (UOI) | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-11-01 | Senior Control System Engineer (Train-13) | 2027-07-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-11-02 | Senior Control System Engineer (SRU) | 2026-09-01 | 2028-04-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-12-01 | Instrument Engineer (SRU) | 2026-12-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-12-02 | Instrument Engineer (Train-13) | 2027-06-15 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-13-01 | Telecom Engineer (Process & SRU) | 2027-03-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-13-02 | Telecom Engineer (Process & SRU) | 2027-05-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-13-03 | Telecom Engineer (UOI) | 2026-11-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-13-04 | Telecom Engineer (UOI) | 2027-01-01 | 2028-05-15 | DHP | B1
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-B-13-05 | Telecom Engineer (UOI) | 2027-02-01 | 2028-04-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-01-01 | Lab Lead Supervisor | 2026-12-01 | 2028-05-31 | EXP | B2
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-01 | Instrument Lead Supervisor (Process) | 2026-07-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-02 | Instrument Lead Supervisor (Train-13) | 2027-06-30 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-03 | Instrument Lead Supervisor (SRU) | 2027-01-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-04 | Instrument Lead Supervisor (UOI) | 2026-11-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-05 | Instrument Lead Supervisor (UOI) | 2026-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-02-06 | Instrument Lead Supervisor (UOI) | 2026-11-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-03-01 | Lab Supervisor | 2027-04-01 | 2028-08-31 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-03-02 | Lab Supervisor | 2027-05-01 | 2028-08-31 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-04-01 | Analyser Supervisor | 2027-06-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-04-02 | Analyser Supervisor | 2026-11-01 | 2028-10-15 | EXP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-01 | Instrument Supervisor (Process) | 2026-11-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-02 | Instrument Supervisor (Process) | 2027-01-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-03 | Instrument Supervisor (Process) | 2027-02-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-04 | Instrument Supervisor (Process) | 2027-03-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-05 | Instrument Supervisor (Process) | 2027-05-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-06 | Instrument Supervisor (Process) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-07 | Instrument Supervisor (Train-13) | 2027-04-15 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-08 | Instrument Supervisor (Train-13) | 2027-07-30 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-09 | Instrument Supervisor (SRU) | 2027-05-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-10 | Instrument Supervisor (UOI) | 2026-04-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-11 | Instrument Supervisor (UOI) | 2026-05-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-12 | Instrument Supervisor (UOI) | 2026-06-01 | 2028-05-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-13 | Instrument Supervisor (UOI) | 2026-07-01 | 2028-06-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-14 | Instrument Supervisor (UOI) | 2026-07-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-15 | Instrument Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-16 | Instrument Supervisor (UOI) | 2027-04-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-17 | Instrument Supervisor (UOI) | 2027-05-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-05-18 | Instrument Supervisor (UOI) | 2027-06-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-06-01 | Control System Supervisor (SRU) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-06-02 | Control System Supervisor (UOI) | 2027-04-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-06-03 | Control System Supervisor (UOI) | 2026-06-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-06-04 | Control System Supervisor (UOI) | 2026-11-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-06-05 | Control System Supervisor (UOI) | 2026-11-01 | 2028-04-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-01 | Telecom Supervisor (Process & SRU) | 2026-10-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-02 | Telecom Supervisor (Process & SRU) | 2027-04-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-03 | Telecom Supervisor (Process & SRU) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-04 | Telecom Supervisor (UOI) | 2026-11-01 | 2028-09-30 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-05 | Telecom Supervisor (UOI) | 2026-12-01 | 2028-05-15 | DHP | C
NFS - SITE | Instrum & CS | PCCSU | PCCSU-15-C-07-06 | Telecom Supervisor (UOI) | 2027-03-01 | 2028-04-30 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-01-01 | Senior Electrical Commissioning Superintendant | 2026-01-01 | 2028-10-15 | EXP | A
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-01 | Electrical Commissioning Superintendant (Process) | 2026-03-01 | 2028-10-15 | EXP | B1
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-02 | Lead Electrical Comm Engineer (cold) | 2026-05-01 | 2028-10-15 | EXP | B1
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-03 | Lead Electrical Comm. Engineer (Train-13) | 2027-05-01 | 2028-10-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-04 | Lead Electrical Comm. Supervisor (Train-13) | 2027-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-05 | Lead Electrical Comm. Engineer (SRU) | 2025-04-01 | 2028-09-30 | DHP | B | Joseph JOHN - TPFQ | ON SITE
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-06 | Electrical Commissioning Superintendant (U&O) | 2025-07-19 | 2028-08-31 | DHP | B | Mahfoud RACHEDI - TPFQ | Under mobilization
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-07 | Lead Electrical Engineer (Offsite&Offplot) | 2026-03-01 | 2028-04-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-02-08 | Lead Electrical Engineer (Inlet) | 2026-07-01 | 2028-04-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-03-01 | Electrical Comm Engineer LOTO | 2026-09-01 | 2028-10-15 | EXP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-03-02 | Electrical Comm Engineer (SRUs) | 2026-03-01 | 2028-04-15 | EXP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-B-03-03 | Electrical Engineer LOTO (UOI) | 2026-05-01 | 2028-04-30 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-16-B-04-01 | Analyser Lead Engineer | 2026-07-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-16-B-05-01 | Analyzer Engineer | 2027-05-01 | 2028-10-15 | DHP | B
NFS - SITE | Instrum & CS | PCCSU | PCCSU-16-B-05-02 | Analyzer Engineer | 2027-02-01 | 2028-10-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-01-01 | Electrical Lead Supervisor (UOI) | 2026-01-01 | 2028-08-31 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-01-02 | Electrical Lead Supervisor (UOI) | 2026-03-01 | 2028-08-31 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-01-03 | Electrical Lead Supervisor (UOI) | 2026-04-01 | 2028-08-31 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-01-04 | Electrical Lead Supervisor (UOI) | 2026-05-01 | 2028-04-30 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-01-05 | Electrical Lead Supervisor (UOI) | 2026-08-01 | 2028-04-30 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-02-01 | Lead Electrical Comm. Supervisor | 2026-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-02-02 | Lead Electrical Comm. Supervisor | 2027-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-01 | Electrical Comm. Supervisor | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-02 | Electrical Comm. Supervisor | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-03 | Electrical Comm. Supervisor | 2026-10-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-04 | Electrical Comm. Supervisor | 2026-10-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-05 | Electrical Comm. Supervisor (Train-13) | 2027-08-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-06 | Electrical Comm. Supervisor (Train-13) | 2027-09-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-07 | Electrical Comm. Supervisor (Train-13) | 2027-11-01 | 2028-10-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-08 | Electrical Comm. Supervisor (SRU) | 2027-04-01 | 2028-09-30 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-09 | Electrical Comm. Supervisor (SRU) | 2027-04-01 | 2028-04-15 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-10 | Electrical Supervisor (UOI) | 2026-05-01 | 2028-04-30 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-11 | Electrical Supervisor (UOI) | 2026-05-01 | 2028-04-30 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-12 | Electrical Supervisor (UOI) | 2026-06-01 | 2028-08-31 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-13 | Electrical Supervisor (UOI) | 2026-07-01 | 2028-08-31 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-14 | Electrical Supervisor (UOI) | 2026-08-01 | 2028-08-31 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-15 | Electrical Supervisor (UOI) | 2026-03-01 | 2028-04-30 | DHP | C
NFS - SITE | Electrical | PCCSU | PCCSU-16-C-03-16 | Electrical Supervisor (UOI) | 2026-08-01 | 2028-04-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-01-01 | MECH Comm. Superintendent | 2026-01-01 | 2028-10-15 | EXP | A
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-01 | Mechanical Lead Engineer ( Ref compressors) | 2026-02-01 | 2028-10-15 | EXP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-02 | Mechanical Lead Engineer (ST compressors) | 2026-11-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-03 | Mechanical Lead Engineer | 2026-11-01 | 2028-10-15 | DHP | B1
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-04 | Mechanical Lead Engineer (Train-13) | 2027-08-01 | 2028-10-15 | EXP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-05 | Mechanical Lead Engineer (SRU) | 2026-08-01 | 2028-09-30 | EXP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-06 | Mechanical Lead Engineer (Utility) | 2026-08-01 | 2028-09-30 | EXP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-07 | Mechanical Lead Engineer (inlet) | 2026-10-01 | 2028-05-31 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-02-08 | Mechanical Lead Engineer (Offsite/Offplot) | 2026-08-01 | 2028-06-30 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-03-01 | Mechanical Comm. Engineer (Train-13) | 2027-09-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-03-02 | Mechanical Engineer (UOI) | 2026-08-01 | 2028-05-31 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-B-03-03 | Mechanical Engineer (UOI) | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-01 | Lead Mechanical Comm. Supervisor (SRU) | 2026-11-01 | 2028-09-30 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-02 | Lead Mechanical Comm. Supervisor (SRU) | 2026-11-01 | 2028-04-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-03 | Mechanical Lead Supervisor (UOI) | 2026-09-01 | 2028-05-31 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-04 | Mechanical Lead Supervisor (UOI) | 2026-11-01 | 2028-06-30 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-05 | Mechanical Lead Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-06 | Lead Mechanical Comm. Supervisor (Process) | 2026-12-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-07 | Lead Mechanical Comm. Supervisor (Process) | 2026-12-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-08 | Lead Mechanical Comm. Supervisor (Train-13) | 2027-05-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-01-09 | Lead Mechanical Comm. Supervisor (Train-13) | 2027-06-01 | 2028-10-15 | DHP | B
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-01 | Mechanical Comm. Supervisor (Process) | 2027-02-01 | 2028-10-15 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-02 | Mechanical Comm. Supervisor (Process) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-03 | Mechanical Comm. Supervisor (Process) | 2027-06-01 | 2028-10-15 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-04 | Mechanical Comm. Supervisor (Train-13) | 2027-08-01 | 2028-10-15 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-05 | Mechanical Comm. Supervisor (SRU) | 2027-06-01 | 2028-09-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-06 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-05-31 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-07 | Mechanical Supervisor (UOI) | 2026-11-01 | 2028-05-31 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-08 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-05-31 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-09 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-06-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-10 | Mechanical Supervisor (UOI) | 2026-11-01 | 2028-09-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-11 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-12 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | C
NFS - SITE | Mechanical | PCCSU | PCCSU-68-C-02-13 | Mechanical Supervisor (UOI) | 2026-08-01 | 2028-09-30 | DHP | C

## NFE Dashboard_Jul 25
Site | Discipline | Dept | Position No | JOB TITLE per manning | BarChart Mob Date | BarChart Demob Date | Entity | Pay Cat | Candidate'a name | Current Mob Step
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-466 | Cybersecurity Technician | 2025-06-01 | 2026-05-31 | DHP | DHP-D | Balaganesh Selvam | 4- MS2 - Waiting for Local contract
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-467 | Cybersecurity Technician | 2025-03-01 | 2026-02-28 | DHP | DHP-D | Abdulkareem Mohieldeen - HUB (Sudanese) Mir Jaffer Ali - HUB (Indian) Balaganesan SElvam | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-468 | Cathodic Protection Specialist | 2025-05-01 | 2025-10-31 | DHP | DHP-B | Shibu Abraham C P | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-469 | Operation Supervisor (Offsites) Day Shift-1 | 2025-06-21 | 2026-06-20 | DHP | DHP-D | JITHUN RAMACHANDRAN | 4- MS2 - Collect of documents
NFE - SITE | O&M | PCCSU | 14.Commissioning-470 | Operation Supervisor (Offsites) Day Shift-2 | 2025-06-21 | 2026-06-20 | DHP | DHP-D | NORIEL S. BICOL | 4- MS4 - QVC required
NFE - SITE | O&M | PCCSU | 14.Commissioning-471 | Operation Supervisor (Offsites) Night Shift-1 | 2025-06-21 | 2026-06-20 | DHP | DHP-D | SYED FURQAN ALI | 4- MS4 - QVC required
NFE - SITE | O&M | PCCSU | 14.Commissioning-472 | Operation Supervisor (Offsites) Night Shift-2 | 2025-06-21 | 2026-06-20 | DHP | DHP-D | MUHAMMED ASIF U | 4- MS2 - Collect of documents
NFE - SITE | O&M | PCCSU | 14.Commissioning-473 | Operation Supervisor (Utility) Day Shift-1 | 2025-06-21 | 2026-06-20 | DHP | DHP-D | MUHAMMAD AMEEN SHAHID. | 4- MS4 - QVC required
NFE - SITE | O&M | PCCSU | 14.Commissioning-474 | Operation Supervisor (Utility) Day Shift-2 | 2025-05-01 | 2026-04-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 2- Rate nego
NFE - SITE | O&M | PCCSU | 14.Commissioning-475 | Operation Supervisor (Utility) Night Shift-1 | 2025-05-01 | 2026-04-30 | DHP | DHP-D | NIKIL THARAYIL | 4- MS3 - Docs submitted for visa application
NFE - SITE | O&M | PCCSU | 14.Commissioning-476 | Operation Supervisor (Utility) Night Shift-2 | 2025-05-01 | 2026-04-30 | DHP | DHP-D | Vineeth Peter | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-477 | PCC Instrument Supervisor - U/O -10 | 2025-06-01 | 2026-07-31 | DHP | DHP-D | MUHAMMED ASSEEM | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-478 | PCC Instrument Supervisor - U/O -11 | 2025-05-01 | 2026-06-30 | DHP | DHP-D | Muhammad Ejaz Khan | 4- MS3 - Docs submitted for visa application
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-479 | PCC Instrument Supervisor - U/O -12 | 2025-05-01 | 2026-06-30 | DHP | DHP-D | Roshan MArk Cullar SAmuel Akhter Arul ASAD | 2- Rate nego
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-480 | PCC Instrument Supervisor - U/O -13 | 2025-05-01 | 2026-09-30 | DHP | DHP-D | Daulet Issagaliyev | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-481 | PCC Instrument Supervisor - U/O -14 | 2025-05-01 | 2026-04-30 | DHP | DHP-D | RAju Murugan | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-482 | PCC Lead Supervisor - Utilities #4 | 2025-06-01 | 2026-04-30 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-483 | PCC Supervisor - Utilities #10 | 2025-06-21 | 2027-03-20 | DHP | DHP-D | Kavi Raj | 4- MS4 - QVC required
NFE - SITE | Process | PCCSU | 14.Commissioning-484 | PCC Supervisor - Utilities #11 | 2025-06-15 | 2026-05-14 | DHP | DHP-D | Bipinkumar DADHANIA | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-485 | PCC Supervisor - Utilities #12 | 2025-06-21 | 2026-05-20 | DHP | DHP-D | G.Antony Bruceley | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-486 | PCC Supervisor - Utilities #13 | 2025-06-01 | 2026-04-30 | DHP | DHP-D | Rico Borbon | 4- MS4 - QVC required
NFE - SITE | Process | PCCSU | 14.Commissioning-487 | PCC Supervisor - Utilities #14 | 2025-06-01 | 2026-04-30 | DHP | DHP-D | Jinesh James | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-488 | PCC Telecom Lead Supervisor (Acciona/Offsite) | 2025-06-01 | 2026-04-30 | DHP | DHP-C | GUO WEI （Vincent Guo） | 2- Rate nego
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-489 | PCC Telecom Supervisor (Acciona/Offsite) #1 | 2025-06-01 | 2026-02-28 | DHP | DHP-D | SD KIM | 2- Rate nego
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-490 | PCC Telecom Supervisor (Acciona/Offsite) #2 | 2025-06-01 | 2026-04-30 | DHP | DHP-D | SUNGUK JUNG | 2- Rate nego
NFE - SITE | O&M | PCCSU | 14.Commissioning-XXX | Night Shift LOTO & Operation Support | 2025-06-01 | 2027-02-28 | DHP | DHP-D | Albert Koshiyev Alonso Patawaran Erwin Ritonga Rustam Batalov Vicor Returnsky | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU |  | System PCC Engineer | 2025-03-01 | 2025-08-31 | DHP |  | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU |  | Electrical PCC Engineer | 2025-03-01 | 2025-08-31 | DHP |  | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-465 | Cathodic Protection Lead Engineer (TBC) | 2025-03-15 | 2026-06-14 | TP | B1 | Marco RECH | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-491 | Commissioning Superintendent HOT Utilities | 2025-07-01 | 2025-11-30 | TP | B1 | Manuel Custodio - NFS | 4- MS2 - Collect of documents
NFE - SITE | Process | PCCSU | 14.Commissioning-491 | Commissioning Superintendent HOT Utilities | 2025-12-01 |  | DHP | DHP-B | Yuni Amri Asmaran Marah - TP HUB Artur Vlasenkov - TP HUB | 2- CV under review
NFE - SITE | Process | PCCSU | 14.Commissioning-492 | Steam blowing specialist | 2025-07-15 | 2025-09-30 | TP | B1 | TBN / Potential NFE internal transfer 1- Sitharth - HUB 2- Roberto Prato - TEN ROC | 2- CV under review
NFE - SITE | Process | PCCSU | 14.Commissioning-492 | Steam blowing specialist | 2025-10-01 | 2025-12-15 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-493 | Process Engineer | 2025-06-01 | 2026-02-28 | TP | C | Boon Ha OOI- TEN | 4- MS2 - Collect of documents
NFE - SITE | O&M | PCCSU | 14.Commissioning-494 | LOTO & Operation Support (NS) - TR-8/10 | 2025-06-01 | 2027-02-28 | DHP | DHP-D | Albert Koshiyev Alonso Patawaran Erwin Ritonga Rustom Battalov Victor Returnskey Nolibert Eligan Ainur Shutayev | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-494.2 | PCC Instrument System Engineer (U/O) | 2025-07-01 | 2026-08-31 | DHP | DHP-C | Nabeel Sarwar Hazem Shana Abdelmadjid Mebirouk | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-495 | PCC Instrument System Engineer (U/O) | 2025-07-01 | 2026-04-30 | DHP | DHP-C | HERY PURWANTO MOTURI.GANAPATHIBABU MOHAMMED MOIN AHMED | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-496 | PCC Instrument System Engineer (U/O) | 2025-07-01 | 2026-04-30 | DHP | DHP-C | PIRAMA NAYAGAM Tariq Iqbal VArghese George Yousef B | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-497 | PCC Instrument System Supervisor (U/O) | 2025-07-01 | 2026-01-31 | DHP | DHP-D | Roshan MArk Cullar SAmuel | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-498 | PCC Instrument System Supervisor (U/O) | 2025-07-01 | 2026-09-30 | DHP | DHP-D | Lindley Galicia Dennis Sanchez Vikas Jawed | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-499 | PCC Instrument System Supervisor (U/O) | 2025-07-01 | 2026-08-31 | DHP | DHP-D | Akhter Arul ASAD | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-437 | Telecom Engineer Lead SV | 2025-03-01 | 2026-12-31 | DHP | DHP-C | Nidheesh Thayyil Ravindran | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-438 | Telecom Lead Supervisor => Telecom lead engineer | 2025-03-01 | 2026-04-30 | TP | B1 | Hocine FASSI | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-439 | Telecom Supervisor | 2025-01-01 | 2026-10-31 | DHP | DHP-D | Mohammad SHAHNEWAZ ALI | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-440 | Telecom Supervisor | 2025-01-01 | 2026-10-31 | DHP | DHP-D | MD Abubakar Ansari | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-441 | INST System Lead Supervisor (U&O) | 2025-07-01 | 2025-11-30 | DHP | DHP-C | Md Eliyas ANWAR | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-442 | INST System Supervisor (U&O) | 2025-07-01 | TBD | DHP | DHP-D | Alex Anto | 2- Waiting for cost approval
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-443 | INST System Supervisor (U&O) | 2024-10-01 | 2025-06-30 | DHP | DHP-D | Rufo Mabunga Balingot | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-128 | PC&C Manager Fresh Water area PC&C Lead Engineer Fresh Water area PC&C Manager Fresh Water area Commissioning Superintendent (U&O) Tr-9/11 Superintendent Desalination area | 2023-10-01 | 2027-04-30 | TP | B1 | Ludovic CLAUDE | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-114 | Commissioning Supervisor- Utilities 1 (U&O) Tr-8/10 #1 | 2023-11-01 | 2027-01-31 | DHP | DHP-D | Manickaraj Dayanidhy-HUB | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-19 | Commissioning Superintendent (Process) Tr-8/10 #1 | 2023-11-20 | 2027-06-30 | CYD | B1 | Ionut Arama | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-137 | Commissioning Supervisor (U&O) Tr-9/11 #2 => Pre-Commissioning & Commissioning Junior Engineer | 2024-01-01 | 2025-12-31 | VIE | TP-E | Faycal ZIANI | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-8 | Commissioning Supporting Team Lead | 2024-01-15 | 2025-04-30 | DHP | DHP-C | Denis Sagadiev | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-450 | Commissioning Lead Supervisor - Fresh Water Area | 2024-12-01 | 2026-01-31 | DHP | DHP-C | Omesh Kumar SAHU | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-456 | Valve Specialist Supervisor - U&O | 2024-12-01 | 2027-06-30 | DHP | DHP-D | KyoungWon Yoon (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-457 | Valve specialist Supervisor - Process | 2025-02-01 | 2027-07-31 | DHP | DHP-D | Manivenkatesh Renganathan | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissionig-425 | SIMOPS Superintendent - Process | 2024-06-01 | 2027-06-30 | DHP | DHP-B | Ngozi Okwuchi NWANKWO | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-1 | Start-up Engineer (Process) | 2025-08-01 | 2027-06-30 | CYD | B2 | N. Watanabe / Y. Shimizu | 2- Waiting for availability confirmation
NFE - SITE | Process | PCCSU | 14.Commissioning-21 | Commissioning Superintendent (Process) Tr-8/10 #3 | 2024-01-25 | 2027-05-31 | CYD | B1 | Dorobantu VASILE | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-101 | Commissioning Spdt (Fresh Water) | 2025-07-01 | 2025-12-31 | DHP | DHP-B | Prabhu VENKATACHALAM | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-105 | Commissioning Lead engineer Supervisor (Utilities) Tr-8/10 #1 | 2023-08-01 | 2027-01-31 | TP | B2 | Pierre FONTAINE | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-106 | Commissioning Lead Supervisor (Utilities) #1 | 2023-09-01 | 2026-08-31 | TP | B2 | Siti Zulaikha BINTI ZABRI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-109 | Commissioning Lead Supervisor (U&O) (JVD)Tr-8/10 #2 Fresh water#1 | 2024-05-01 | 2025-07-10 | DHP | DHP-C | Valeriy Teron (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-109 | Commissioning Lead Supervisor Fresh water#1 | 2025-07-11 | 2025-11-30 | DHP | DHP-C | Surendran Mannoopurayidathil Raveendran(HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-110 | Commissioning Lead Supervisor (Inlet) 1 (JVD)Tr-8/10 #3 | 2024-05-01 | 2027-01-14 | DHP | DHP-C | Stephen Babu Katuri(HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-111 | Commissioning Lead Supervisor (Offsites) 1 (JVD)Tr-8/10 #4 | 2024-06-01 | 2027-01-31 | DHP | DHP-C | Dan Mugurel Padurariu | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-112 | Commissioning Lead Supervisor (Offsites) 2 (JVD)Tr-8/10 #5 | 2024-07-01 | 2026-08-31 | DHP | DHP-C | Ramdas Raghunath Langhe | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-20 | Commissioning Superintendent (Process) Tr-8/10 #2 | 2024-01-31 | 2027-06-30 | CYD | B1 | Sandu Oleg | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-38 | Commissioning Supervisor Utilities (Process) Tr-8/10 #2 | 2024-02-01 | 2027-06-30 | TP | C | Dedy Ehsanudin- potential replacement (from Aug 2025) Laurana BELORGANE - TP POC P381 | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-10 | Commissioning Supporting Supervisor #2 | 2025-06-01 | 2027-05-31 | DHP | DHP-D | Muhammad Fareed | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-119 | Commissioning Supervisor Utilities 5 (U&O) Tr-8/10 #6 | 2024-06-01 | 2027-04-30 | DHP | DHP-D | Praveen Punnor Prabhakaran | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-115 | Commissioning Supervisor process Fresh water 1 (U&O) Tr-8/10 #2 | 2024-07-01 | 2025-11-30 | DHP | DHP-D | Tanaji AGUNDE | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-39 | Commissioning Supervisor (Process) Tr-8/10 #3 | 2024-07-01 | 2026-11-30 | DHP | DHP-D | Roy Palma Tranate | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-118 | Commissioning Supervisor Utilities 4 (U&O) Tr-8/10 #5 | 2024-08-01 | 2027-05-31 | DHP | DHP-D | Sujeesh Palliyali | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-12 | Commissioning Material Coordinator | 2024-08-01 | 2027-05-31 | DHP | DHP-E | Olga LI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-120 | Commissioning Supervisor-Offsites 1 (U&O) Tr-8/10 #7 | 2024-08-01 | 2025-07-10 | DHP | DHP-D | Surendran Mannoopurayidathil Raveendran(HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-120 | Commissioning Supervisor-Offsites 1 | 2025-07-11 | 2026-05-31 | DHP | DHP-D | Felix Raj | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-117 | Commissioning Supervisor Fresh Water Utilities 3 (U&O) Tr-8/10 #4 - Fresh water | 2024-09-01 | 2026-11-30 | DHP | DHP-D | Ram SAROOP (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-48 | Commissioning Supervisor (Process) Tr-8/10 #12 | 2024-09-01 | 2026-11-30 | DHP | DHP-D | Vaibhav Anil JADHAV | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-108 | Commissioning Superintendent-Utilities | 2024-10-01 | 2026-11-30 | DHP | DHP-B | Santhosh Punnoor Prabhakaran | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-122 | Commissioning Supervisor (Inlet) #1 (U&O) Tr-8/10 #9 | 2024-10-01 | 2027-04-30 | DHP | DHP-D | Muhammed Amjad | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-129 | Commissioning Lead Engineer Inlet (Utilities) #2(U&O) Tr-9/11 | 2024-04-15 | 2026-06-14 | TP | B1 | Aymen KHLIFI - TEN POC | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-13 | Commissioning Material Supporting Supervisor #1 #3 | 2025-02-01 | 2027-06-30 | DHP | DHP-D | Mehdi MEZIANI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-130 | Commissioning Engineer -offsites #1(U&O) Tr-9/11 #1 | 2024-04-01 | 2025-12-31 | TP | B2 | Gauthier Vanhee | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-132 | Commissioning Lead Supervisor (Inlet)2 (U&O) Tr-9/11 #1 | 2024-11-01 | 2027-05-31 | DHP | DHP-C | Manolette Pumatong Manalo | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-133 | Commissioning Lead Supervisor -(Utilities) #3 | 2025-02-01 | 2025-05-04 | DHP | DHP-C | Manikandan Annamalai | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-133 | Commissioning Lead Supervisor -(Utilities) #3 | 2025-06-01 | 2027-04-30 | DHP | DHP-C | 1- IRWAN IRAWAN 2-Syamsul Rizal Fauzi | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-40 | Commissioning Supervisor (Process) Tr-8/10 #4 | 2024-10-01 | 2027-06-30 | DHP | DHP-D | Dexie Pailagao ANTIQUESA | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-41 | Commissioning Supervisor (Process) Tr-8/10 #5 | 2024-10-01 | 2025-05-31 | DHP | DHP-D | Mohamed Shakir HUSSAIN | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-41 | Commissioning Supervisor (Process) Tr-8/10 #5 | 2025-05-04 | 2027-06-30 | DHP | DHP-D | Xavier Sugin John Joseph Arulmani | 4- MS2 - Collect of documents
NFE - SITE | Process | PCCSU | 14.Commissioning-42 | Commissioning Supervisor (Process) Tr-8/10 #6 | 2024-10-01 | 2027-05-31 | DHP | DHP-D | Sukma Rifki | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-138.2 | Pre-Commissioning & Commissioning Junior Engineer | 2024-01-01 | 2025-12-31 | VIE | TP-E | Anne MOUTHOU | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-14 | Commissioning Material Supervisor #2 | 2025-04-01 | 2027-01-31 | DHP | DHP-D | ALLAN RITO DELOS SANTOS TORRES | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-141 | ELE Comm. Superintendent Tr-8/9/10/11 | 2023-04-01 | 2027-02-28 | TP | B1 | Leong Peng YEOW - KL/GC HUB | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-142 | ELE Comm. Deputy Superintendent Tr-8/9/10/11 | 2024-04-01 | 2027-06-30 | CYD | B1 | Yuhei Aoki | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-143 | ELE Lead Engineer (Process) Tr-8/10 | 2024-02-04 | 2027-05-31 | CYD | B1 | Seiya Iguchi | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-144 | ELE Engineer (Process) Tr-8/10 #1 | 2024-04-01 | 2026-11-30 | DHP | DHP-C | Natarajan Muthu Valliappan | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-145 | ELE Engineer (Process) Tr-8/10 #2 | 2024-05-01 | 2026-11-30 | DHP | DHP-C | Sagar Jagadale | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-146 | ELE Lead Supervisor (Process) Tr-8/10 #1 | 2023-08-01 | 2027-01-31 | DHP | DHP-C | Sridhar Ponnusamy | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-147 | ELE Lead Supervisor (Process) Tr-8/10 #2 | 2024-03-01 | 2026-07-31 | DHP | DHP-C | Victor TUSCANO | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-148 | ELE Lead Supervisor (Process) Tr-8/10 #3 | 2024-04-01 | 2025-06-23 | DHP | DHP-C | Srinivas Reddy Pilaka | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-148 | ELE Lead Supervisor (Process) Tr-8/10 #3 | 2025-07-01 | 2026-08-31 | DHP | DHP-C | SAravanan Dmitriy Drinitsin Rajmohan Ganesan | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-149 | ELE Engineer (Process) Tr-8/10 #3 | 2024-03-01 | 2025-05-20 | DHP | DHP-C | Satish Kumar | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-149 | ELE Engineer (Process) Tr-8/10 #3 | 2025-05-01 | 2026-07-31 | DHP | DHP-C | Bharathi RAja | 4- MS2 - Waiting for Local contract
NFE - SITE | Material | PCCSU | 14.Commissioning-15 | Commissioning Scaffolding Coordinator #1 Commissioning Material Coordinator #2 | 2025-05-15 | 2027-07-31 | DHP | DHP-E | Enrique Napuran Gingco | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-150 | ELE Supervisor (Process) Tr-8/10 #1 | 2024-10-01 | 2026-01-31 | DHP | DHP-D | Abdul FATHAH | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-151 | ELE Supervisor (Process) Tr-8/10 #2 | 2025-07-01 | 2027-04-30 | DHP | DHP-D | Venkata Durgarao | 4- MS4 - QVC required
NFE - SITE | Electrical | PCCSU | 14.Commissioning-152 | ELE Supervisor (Process) Tr-8/10 #3 | 2024-11-01 | 2026-08-31 | DHP | DHP-D | Satya Lakkaju | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-153 | ELE Lead Supervisor (Process) Tr-8/10 #4 | 2024-10-01 | 2027-03-31 | DHP | DHP-C | Amitkumar Dilipbhai Shah | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-154 | Electrical Substation Supervisor (Process) Tr-8/10 #1 | 2024-07-01 | 2027-01-01 | DHP | DHP-D | NITIN KASHINATH MHARAV | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-155 | Electrical Substation Supervisor (Process) Tr-8/10 #2 | 2024-07-14 | 2026-09-30 | DHP | DHP-D | Manikandan Murugan - CTJV 2352 | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-156 | Electrical Substation Supervisor (Process) Tr-8/10 #3 | 2024-10-01 | 2026-09-30 | DHP | DHP-D | Kenneth Guban | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-157 | ELE Lead Engineer (U&O) Tr-8/10 | 2024-11-01 | 2025-07-06 | DHP | DHP-C | Mahesh Babu thalari - CTJV TP => CTJV CH | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-157 | ELE Lead Engineer (U&O) Tr-8/10 | 2025-07-07 | 2025-10-31 | DHP | DHP-C | Benny Chen Chacko | 2- Waiting for availability confirmation
NFE - SITE | Electrical | PCCSU | 14.Commissioning-158 | ELE Engineer (U&O) Tr-8/10 #1 | 2023-12-16 | 2026-12-15 | TP | B2 | Ikram CHOUBARI | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-159 | ELE Engineer (U&O) Tr-8/10 #2 | 2024-01-14 | 2026-07-31 | DHP | DHP-C | Muhammad ZULFARHAN Bin HAMDAN | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-16 | Commissioning Scaffolding Coordinator #2 Commissioning Temporaries Coordinator #3 | 2024-12-01 | 2027-04-30 | DHP | DHP-E | Gireesh Kumar Jeevan Edgar Uday Kamaladdin M Fareed | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-160 | ELE Lead Supervisor (U&O) Tr-8/10 #1 | 2024-05-01 | 2026-06-30 | DHP | DHP-C | Sanu Alathra Varghese | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-161 | ELE Lead Supervisor (U&O) Tr-8/10 #2 | 2023-08-01 | 2026-09-30 | DHP | DHP-C | Mohamed IDRIS BinMd Kamal- HUB | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-162 | ELE Lead Supervisor (U&O) Tr-8/10 #3 | 2024-02-15 | 2027-01-31 | DHP | DHP-C | Gerald Olegario Gonzales | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-163 | ELE Lead Supervisor (U&O) Tr-8/10 #4 | 2024-10-21 | 2027-03-31 | DHP | DHP-C | Mark Gerald DE LEON MAPOY | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-164 | ELE Supervisor (U&O) Tr-8/10 #1 | 2024-05-01 | 2026-12-31 | DHP | DHP-D | Mohammad Shahanshah Alam - HUB | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-165 | ELE Supervisor (U&O) Tr-8/10 #2 | 2024-05-01 | 2026-11-30 | DHP | DHP-D | Abdul Razak Perumparambil - HUB | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-166 | ELE Supervisor (U&O) Tr-8/10 #3 | 2024-10-01 | 2027-02-28 | DHP | DHP-D | Rhodora Viray CAÑAMAQUE | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-167 | ELE Supervisor (U&O) Tr-8/10 #4 | 2024-07-01 | 2026-11-30 | DHP | DHP-D | Faisal Nondathu Parambil Hydrose | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-168 | ELE Supervisor (U&O) Tr-8/10 #5 | 2025-01-01 | 2026-03-31 | DHP | DHP-D | Iyappan Shunmugasundaravel (HUB) | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-169 | ELE Supervisor (U&O) Tr-8/10 #6 | 2025-02-01 | 2026-04-30 | DHP | DHP-D | Pragneshkumar RAJPUT | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-17 | Commissioning Temporaries Coordinator #1 | 2024-10-01 | 2027-07-31 | DHP | DHP-E | Sajid Anjum | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-170 | ELE Supervisor (U&O) Tr-8/10 #7 | 2025-01-01 | 2026-08-31 | DHP | DHP-D | Mohammed Yasser Ali Ahamed Basheer | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-171 | ELE Supervisor (U&O) Tr-8/10 #8 | 2025-04-01 | 2025-10-31 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-172 | Electrical Substation Supervisor (U&O) Tr-8/10 #1 | 2024-05-01 | 2026-07-31 | DHP | DHP-D | Berlin Pagcaliwagan Fortuna (HUB) | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-173 | Electrical Substation Supervisor (U&O) Tr-8/10 #2 | 2024-04-01 | 2026-09-30 | DHP | DHP-D | Ronaldo Arquillo Castenada | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-174 | Electrical Substation Supervisor (U&O) Tr-8/10 #3 | 2024-12-01 | 2027-02-28 | DHP | DHP-D | Rommel Carias Guzman | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-175 | Electrical Substation Supervisor (U&O) Tr-8/10 #4 | 2025-01-01 | 2026-10-31 | DHP | DHP-D | Jayeshkumar Shantilal Patel | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-176 | Electrical Substation Supervisor (U&O) Tr-8/10 #5 | 2024-12-01 | 2026-01-31 | DHP | DHP-D | 1-Sashikanta Mohali (HUB) | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-177 | Electrical Substation Supervisor (U&O) Tr-8/10 #6 | 2025-07-01 | 2026-06-30 | DHP | DHP-D | MOHAMMAD ASGHER ALI | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-178 | ELE Comm. Lead Engineer #1 Tr-9/11 | 2025-04-01 | 2025-07-05 | CYD | B1 | Yoshihiko UMENO | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-178 | ELE Comm. Lead Engineer #1 Tr-9/11 | 2025-07-05 | 2027-04-30 | CYD | B1 | TBD | 2- Waiting for availability confirmation
NFE - SITE | Electrical | PCCSU | 14.Commissioning-179 | ELE Comm. Lead Engineer #2 Tr-9/11 | 2024-05-01 | 2026-07-31 | TP | B1 | Renju Cherian - KL / HUB | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-18 | Commissioning Temporaries Coordinator #2 | 2024-11-01 | 2027-04-30 | DHP | DHP-E | Umesh pullanikkattu parambil | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-180 | ELE Lead Engineer (Process) Tr-9/11 | 2025-01-01 | 2027-06-30 | CYD | B2 | Eiki Taniguchi | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-181 | ELE Engineer (Process) Tr-9/11 #1 | 2025-03-01 | 2027-02-01 | CYD | DHP-C | Chrisanto C. BALLECER | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-182 | ELE Engineer (Process) Tr-9/11 #2 | 2025-06-15 | 2027-07-31 | DHP | DHP-C | Akylbek Zhexembiyev | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-183 | ELE Lead Supervisor (Process) Tr-9/11 #1 | 2025-03-01 | 2027-06-30 | DHP | DHP-C | Jehieli Luzares Sausa | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-184 | ELE Lead Supervisor (Process) Tr-9/11 #2 | 2025-02-01 | 2027-02-28 | DHP | DHP-C | Herry Irawan | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-185 | ELE Lead Supervisor (Process) Tr-9/11 #3 | 2025-04-01 | 2026-10-31 | DHP | DHP-C | Syamsul Hidayat | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-186 | ELE Supervisor (Process) Tr-9/11 #1 | 2025-09-01 | 2027-06-30 | DHP | DHP-D | Pritesh Subham Athos | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-187 | ELE Supervisor (Process) Tr-9/11 #2 | 2025-07-01 | 2026-12-31 | DHP | DHP-D | FARITH ASHIK RAHMAN | 3- Waiting for PAF/PAAF issuance
NFE - SITE | Process | PCCSU | 14.Commissioning-49 | Commissioning Supervisor (Process) Tr-8/10 #13 | 2024-10-01 | 2027-01-31 | DHP | DHP-D | Mandar Shashikant RANDIVE | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-190 | Electrical Substation Supervisor (Process) Tr-9/11 #1 | 2025-05-01 | 2027-04-30 | DHP | DHP-D | Bryan James XAvier Mohamed ZAhid Alam James Raja Parthiban REnato Pajarillo | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-191 | Electrical Substation Supervisor (Process) Tr-9/11 #2 | 2025-04-01 | 2027-01-31 | DHP | DHP-D | Rameshkumar S | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-192 | Electrical Substation Supervisor (Process) Tr-9/11 #3 | 2025-05-01 | 2026-03-31 | DHP | DHP-D | Sadham Hussain Sulthan Hameed | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-193 | ELE Lead Supervisor (U&O) Tr-9/11 | 2025-03-01 | 2026-11-30 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-194 | ELE Engineer (U&O) Tr-8/9/10/11 | 2024-06-01 | 2027-04-30 | DHP | DHP-C | Kannan Moorthy(HUB) | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-195.1 | ELE Lead Supervisor (U&O) Tr-9/11 => Pre-Commissioning & Commissioning junior Engineer (Electrical) | 2024-05-01 | 2026-04-30 | VIE | TP-E | Badr BOULBAIR | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-52 | Commissioning Supervisor (Process) Tr-8/10 #16 | 2024-10-01 | 2027-04-30 | DHP | DHP-D | Dheeraj Kumar Verma | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-195.2 | ELE Lead Supervisor (U&O) Tr-9/11=> Pre-Commissioning & Commissioning junior Engineer (Electrical) | 2024-10-01 | 2026-09-30 | VIE | TP-E | Ousmane SIBY | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-196 | ELE Supervisor (U&O) Tr-9/11 #1 | 2025-08-01 | 2027-06-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-197 | ELE Supervisor (U&O) Tr-9/11 #2 | 2026-03-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Electrical | PCCSU | 14.Commissioning-198 | ELE Supervisor (U&O) Tr-9/11 #3 | 2024-09-01 | 2025-11-30 | DHP | DHP-D | Swaminathan GOPALAN | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-199 | ELE Supervisor (U&O) Tr-9/11 #4 | 2025-01-01 | 2026-03-31 | DHP | DHP-D | Mohamed Jasir Mohamed Meerasha | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-2 | Start-up Engineer (U&O) #1 => O&M engineer | 2025-04-01 | 2026-09-30 | TP | B2 | Lina Manali Zebadi - TEN | 5- Mobilized
NFE - SITE | Material | PCCSU | 14.Commissioning-9 | Commissioning Supporting Supervisor #1 | 2024-10-01 | 2027-01-31 | DHP | DHP-D | Raymond Ignacio Domingo | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-200 | Electrical Substation Supervisor (U&O) Tr-9/11 #1 | 2025-02-01 | 2027-05-31 | DHP | DHP-D | Shashikanta Mohali - HUB | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-201 | Electrical Substation Supervisor (U&O) Tr-9/11 #2 | 2025-07-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-202 | INST Comm. Superintendent Tr-8/9/10/11 | 2024-09-01 | 2027-06-30 | CYD | B1 | Katsushi Shibata | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-203 | INST Comm. Deputy Superintendent Tr-8/9/10/11 | 2024-08-28 | 2027-07-31 | TP | B1 | Samer AYOUBI - HUB/TPFQ | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-204 | INST Lead Engineer (Process) Tr-8/10 | 2024-07-25 | 2027-05-31 | CYD | B1 | Ryutaro TAKADA | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-205 | INST Engineer (Process) Tr-8/10 #1 | 2024-06-01 | 2027-06-30 | CYD | DHP-C | Vivian Afroilan | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-206 | INST Engineer (Process) Tr-8/10 #2 | 2024-08-01 | 2026-11-30 | DHP | DHP-C | Yulia Mifthah Al Jannah | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-207 | INST Engineer (Process) Tr-8/10 #3 | 2024-12-01 | 2027-01-31 | DHP | DHP-C | Eriberto Dipasupil ADALIA | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-208 | INST Lead Supervisor (Process) Tr-8/10 #1 | 2024-11-01 | 2025-06-12 | DHP | DHP-C | Tulegen Yerdynbekov | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-208 | INST Lead Supervisor (Process) Tr-8/10 #1 | 2025-07-01 | 2027-03-31 | DHP | DHP-C | Darwin Magbuhat Panopio | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-209 | INST Lead Supervisor (Process) Tr-8/10 #2 | 2024-11-01 | 2026-11-30 | DHP | DHP-C | Arnel FRANCO RICOHERMOSO | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-53 | Commissioning Supervisor (Process) Tr-8/10 #17 | 2024-11-01 | 2026-12-31 | DHP | DHP-D | Sudhir Utaker | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-210 | INST Lead Supervisor (Process) Tr-8/10 #3 | 2025-01-01 | 2026-11-30 | DHP | DHP-C | Rubelito Pana TURNOAS | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-211 | INST Supervisor (Process) Tr-8/10 #1 | 2024-08-15 | 2027-03-15 | DHP | DHP-D | Hadje P Calimotan | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-212 | INST Supervisor (Process) Tr-8/10 #2 | 2024-09-01 | 2027-01-31 | DHP | DHP-D | Antonio Francisco Pangilinan Adajar | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-213 | INST Supervisor (Process) Tr-8/10 #3 | 2024-10-01 | 2026-11-30 | CYD | DHP-D | JHEREMY MACH CORPUZ | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-214 | INST Supervisor (Process) Tr-8/10 #4 | 2024-10-01 | 2026-11-30 | CYD | DHP-D | MARK LORENCE BILLONES | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-215 | INST Supervisor (Process) Tr-8/10 #5 | 2024-12-01 | 2026-10-31 | DHP | DHP-D | Amar Muhammad | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-22 | Commissioning Lead Engineer(Process) Tr-8/10 #1 => commissioning Manager (Process) | 2023-11-01 | 2027-05-31 | CYD | B1 | Hongliang Zhang | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-223 | INST System Lead Engineer (Process) Tr-8/10 | 2024-04-01 | 2027-03-31 | CYD | B1 | Guston Supriadi | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-224 | Senior INST System Engineer (Process) Tr-8/10 #1 | 2025-07-01 | 2027-06-30 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-226 | Senior INST System Engineer (Process) Tr-8/10 #3 | 2024-11-01 | 2026-12-31 | DHP | DHP-B | Jan Johannes Stephanus NEL | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-227 | INST System Engineer (Process) Tr-8/10 #1 | 2024-11-01 | 2027-05-31 | DHP | DHP-C | Muhammad Thariq Hadad | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-228 | INST System Engineer (Process) Tr-8/10 #2 | 2024-06-01 | 2027-06-30 | DHP | DHP-C | Joji Joseph | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-229 | INST System Engineer (Process) Tr-8/10 #3 | 2024-09-01 | 2026-11-30 | DHP | DHP-C | Satish Baburao Chougle | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-23 | Commissioning Lead Engineer(Process) Tr-8/10 #2 | 2023-05-11 | 2027-03-31 | CYD | B1 | Takahiro Shimada | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-230 | INST System Engineer (Process) Tr-8/10 #4 | 2024-09-01 | 2026-12-31 | DHP | DHP-C | Hari Kusnomo Bn Suwari KARTO | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-231 | INST System Engineer (Process) Tr-8/10 #5 = > => Instrument Lead Supervisor(Process) | 2025-06-01 | 2027-06-30 | DHP | DHP-C | Esa Pratiwi Suryaningtyas | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-232 | INST System Supervisor (Process) Tr-8/10 #1 | 2024-10-01 | 2027-05-31 | DHP | DHP-D | Ferdinand VILLA DIRAIN | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-233 | INST System Supervisor (Process) Tr-8/10 #2 | 2024-10-01 | 2027-05-31 | DHP | DHP-D | Venkata Ramana Kalisetty | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-234 | Analyzer Engineer (Process) Tr-8/10 #1 | 2024-10-01 | 2025-10-31 | CYD | DHP-D | DOHN ALVIN RODRIGUEZ | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-235 | Analyzer Engineer Supervisor(Process) Tr-8/10 #2 | 2026-01-01 | 2026-11-30 | DHP | DHP-D | 1-Sunil Vincent 2-Mark Cullar 3-Rajendran 4-Saurav Singh 5-Waqas Tahir 6-Advin Ceasar 7-Azizol Bin Ramli 8-MUHAMMAD FIAZ 9-Ganesan 10-Rizwan riaz | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-236 | INST Lead Engineer (U&O) Tr-8/10 | 2024-07-15 | 2027-05-31 | DHP | DHP-B | Ronie Cabangbang Alilin | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-237 | INST Engineer (U&O) Tr-8/10 | 2025-07-01 | 2027-03-31 | DHP | DHP-C | Papanaidu VATICULDALA | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-238 | INST Engineer (U&O) Tr-8/10 #2 | 2024-10-01 | 2027-01-31 | TP | C | Adi OPIJAC | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-239 | INST Engineer (U&O) Tr-8/10 #3 | 2024-08-19 | 2026-11-30 | TP | C | Abdulhamed Nasrullah - TEN UK | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-24 | Commissioning Lead Engineer(Process) Tr-8/10 #3 | 2024-03-01 | 2027-06-30 | CYD | B1 | Glenn Mark SIIOCO ALOLOR | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-240 | INST Lead Supervisor (U&O) Tr-8/10 #1 | 2024-10-01 | 2027-07-31 | DHP | DHP-C | JayeshKumar Narsinhbhai Bhagat | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-241 | INST Lead Supervisor (U&O) Tr-8/10 #2 | 2024-04-01 | 2027-02-28 | DHP | DHP-C | Sameer HUSSAIN (KL - HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-242 | INST Lead Supervisor (U&O) Tr-8/10 #3 | 2024-02-01 | 2026-11-30 | DHP | DHP-C | Mohammed Jawed | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-244 | INST Supervisor (U&O) Tr-8/10 #1 | 2024-05-01 | 2027-02-28 | DHP | DHP-D | Jayavinesh Jayaraj | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-245 | INST Supervisor (U&O) Tr-8/10 #2 | 2025-05-01 | 2026-12-31 | DHP | DHP-D | Lindley Galicia Dennis Sanchez Vikas Jawed | 4- MS2 - Collect of documents
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-246 | INST Supervisor (U&O) Tr-8/10 #3 | 2025-06-01 | 2027-01-31 | DHP | DHP-D | SHERWIN C. ALFONSO | 4- MS4 - QVC required
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-247 | INST Supervisor (U&O) Tr-8/10 #4 | 2024-07-01 | 2027-01-31 | DHP | DHP-D | Zaldy Bugais Balilihan (HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-248 | INST Supervisor (U&O) Tr-8/10 #5 | 2025-07-01 | 2027-01-31 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-249 | INST Supervisor (U&O) Tr-8/10 #6 | 2024-09-01 | 2025-12-31 | DHP | DHP-D | Vipindas PANENTAVIDA | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-25 | Commissioning Engineer (Process) Tr-8/10 #1 | 2024-07-01 | 2027-05-31 | CYD | B2 | Takashi Miyamoto | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-250 | INST Supervisor (U&O) Tr-8/10 #7 | 2024-10-01 | 2025-12-31 | DHP | DHP-D | Baurzhan Nauanov | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-256 | Analyzer Engineer (U&O) Tr-8/10 | 2024-08-01 | 2026-11-30 | DHP | DHP-C | Ruslan Khaertdinov (HUB)- | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-257 | INST System Superintendent Lead Engineer (U&O) Tr-8/10 | 2024-01-01 | 2027-01-31 | TP | B1 | Xavier DAVION | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-258 | Senior INST System Engineer (U&O) Tr-8/10 #1 | 2023-12-15 | 2026-11-30 | DHP | DHP-B | Nikhil Shivaji MORE | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-259 | Senior INST System Engineer (U&O) Tr-8/10 #2 | 2024-02-15 | 2026-11-30 | DHP | DHP-B | Urdanito Jr Empleo Doliente (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-26 | Commissioning Engineer (Process) Tr-8/10 #2 | 2024-12-01 | 2027-07-31 | CYD | B2 | Eisuke Tanaka | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-260 | Senior INST System Engineer (U&O) Tr-8/10 #3 | 2025-02-01 | 2027-02-28 | DHP | DHP-B | Biswajit CHAKRABORTY | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-261 | Senior INST System Engineer (U&O) Tr-8/10 #4 | 2025-02-01 | 2026-02-28 | DHP | DHP-B | Muraleedharan Asari Kunjukrishnan Asari | 4- MS4 - Waiting for hotel booking/site arrangements
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-262 | INST System Engineer (U&O) Tr-8/10 #1 | 2024-04-01 | 2027-03-31 | DHP | DHP-C | Srinath GANESAN (HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-263 | INST System Engineer (U&O) Tr-8/10 #2 | 2024-10-01 | 2026-10-15 | DHP | DHP-C | Shine Kaithappillil Ouso | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-264 | INST System Engineer (U&O) Tr-8/10 #3 | 2024-09-01 | 2027-01-31 | DHP | DHP-C | Subin Komattupeedikayil Thomas(HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-265 | INST System Engineer (U&O) Tr-8/10 #4 | 2024-09-01 | 2026-12-31 | TP | C | Reza Danesh Zad Moghadam | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-266 | INST System Engineer (U&O) Tr-8/10 #5 | 2024-10-01 | 2026-01-31 | DHP | DHP-C | Jenefer HILLARY BERNARD (HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-267 | INST System Engineer (U&O) Tr-8/10 #6 | 2024-12-01 | 2026-03-31 | DHP | DHP-C | Vishal Shivaji Choudhari | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-268 | INST System Engineer (U&O) Tr-8/10 #7 | 2025-03-01 | 2026-11-30 | DHP | DHP-C | Vinoth Ravichandiran | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-269 | INST System Engineer (U&O) Tr-8/10 #8 | 2025-03-01 | 2026-11-30 | DHP | DHP-C | Rajesh SIVANESAN | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-27 | Commissioning Engineer (Process) Tr-8/10 #3 | 2024-10-01 | 2027-06-30 | CYD | B2 | Kazuya OTANI | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-270 | INST System Supervisor (U&O) Tr-8/10 #1 | 2024-04-15 | 2027-04-30 | DHP | DHP-D | Sunilkumar Amrutlal Patel | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-271 | INST System Supervisor (U&O) Tr-8/10 #2 | 2024-08-01 | 2026-06-30 | DHP | DHP-D | Ulysses Myco Cajan Doliente | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-272.1 | Analyzer Engineer Tr-8/9/10/11 #1 | 2024-10-01 | 2027-04-30 | DHP | DHP-C | Ashiq Hussain (HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-272.2 | Lab Engineer Tr-8/9/10/11 #2 | 2025-02-01 | 2027-05-31 | DHP | DHP-C | 1-Abdelhalim Boukraa-HUB 2-Navasdeen Ali Akbar-HUB | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-273 | Lab Engineer Tr-8/9/10/11 #2 | 2024-06-01 | 2025-12-31 | DHP | DHP-C | Lay Mee Ping - HUB | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-274 | Lab Supervisor Tr-8/10 #1 | 2025-02-01 | 2027-07-31 | DHP | DHP-D | Mahesh Venktayya Devadiga | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-275 | Lab Supervisor Tr-8/10 #2 | 2025-06-15 | 2026-11-14 | DHP | DHP-D | AJITH KUMAR SUNDAR RAJ | 4- MS4 - QVC required
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-276 | Lab Supervisor Tr-8/10 #3 | 2024-12-01 | 2026-12-31 | DHP | DHP-D | Gianni Christy Sarkissian | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-277 | INST Comm. Lead Engineer #1 Tr-9/11 | 2025-06-01 | 2027-01-31 | TP | B1 | Waseem Omran | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-278 | INST Comm. Lead Engineer #2 Tr-9/11 | 2025-02-01 | 2027-05-31 | CYD | B1 | Tomohiro Yoshimi | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-279 | INST Lead Engineer (Process) Tr-9/11 | 2024-11-01 | 2026-11-30 | CYD | B1 | Abhishek Mittal | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-28 | Commissioning Engineer (Process) Tr-8/10 #4 | 2023-11-11 | 2025-07-24 | DHP | DHP-C | Catur Pamularsih - CTJV TP | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-28 | Commissioning Engineer (Process) Tr-8/10 #4 | 2025-07-25 | 2027-01-31 | DHP | DHP-C | Mark Adrian W. Pelagio | 3- Waiting for PAF/PAAF signed
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-280 | INST Engineer (Process) Tr-9/11 #1 => PCC Instrument Supervisor | 2025-06-15 | 2027-04-14 | DHP | DHP-D | Razhdi Cabaluna | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-281 | INST Engineer (Process) Tr-9/11 #2 => INST System Engineer (Process) Tr-9/11 #2 | 2025-05-01 | 2027-06-30 | DHP | DHP-C | ANDI SAEHUL RIZAL | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-282 | INST Engineer (Process) Tr-9/11 #3 | 2024-12-01 | 2027-04-30 | DHP | DHP-C | Jowie O. Basas | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-283 | INST Lead Supervisor (Process) Tr-9/11 #1 | 2025-07-01 | 2026-06-30 | DHP | DHP-D | MARK CHRISTIAN PLACIDO | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-284 | INST Lead Supervisor (Process) Tr-9/11 #2 | 2025-06-21 | 2027-04-20 | DHP | DHP-C | Bernie Gabisan | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-285 | INST Lead Supervisor (Process) Tr-9/11 #3 | 2025-08-01 | 2026-07-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-286 | INST Supervisor (Process) Tr-9/11 #1 | 2025-02-01 | 2027-03-31 | DHP | DHP-D | Radityasih Ambarini | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-287 | INST Supervisor (Process) Tr-9/11 #2 | 2025-02-01 | 2027-04-30 | DHP | DHP-D | Haidar Ubaidillah | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-288 | INST Supervisor (Process) Tr-9/11 #3 | 2025-02-01 | 2027-05-31 | DHP | DHP-D | Omar Abdussaid | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-29 | Commissioning Engineer (Process) Tr-8/10 #5 | 2024-11-15 | 2027-02-14 | CYD | DHP-C | Isaiah A. De Leon | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-293 | Analyzer Engineer (Process) Tr-9/11 => Analyzer Supervisor (U&O) | 2025-02-07 | 2026-05-31 | DHP | DHP-D | RAJESWAREN BALACHENDRAN | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-296 | INST System Lead Engineer (Process) Tr-9/11 | 2024-07-09 | 2027-01-08 | CYD | B1 | Nishioka, Keisuke | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-297 | Senior INST System Engineer (Process) Tr-9/11 #1 | 2025-11-01 | 2027-01-31 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-298 | Senior INST System Engineer (Process) Tr-9/11 #2 | 2025-06-01 | 2026-07-31 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-299 | Senior INST System Engineer (Process) Tr-9/11 #3 | 2026-06-01 | 2027-06-30 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-30 | Commissioning Engineer (Process) Tr-8/10 #6 | 2025-02-01 | 2026-12-31 | DHP | DHP-C | Vikranth Katta | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-300 | Senior INST System Engineer (Process) Tr-9/11 #4 | 2025-11-01 | 2026-10-31 | DHP | DHP-B | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-301 | INST System Engineer (Process) Tr-9/11 #1 | 2025-07-01 | 2026-12-31 | DHP | DHP-C | Yaya Sunarya? | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-302 | INST System Engineer (Process) Tr-9/11 #2 => Lead Instrument Supervisor | 2025-04-01 | 2027-05-31 | DHP | DHP-C | Ronnel Tolentino Guico | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-303 | INST System Engineer (Process) Tr-9/11 #3 | 2025-04-01 | 2027-05-31 | DHP | DHP-C | Tito Junior Fabrigas Villegas | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-304 | INST System Supervisor (Process) Tr-9/11 #3 | 2025-07-01 | 2027-03-31 | DHP | DHP-D | Denny Pramudibyo. N | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-305 | INST System Supervisor (Process) Tr-9/11 #1 | 2025-09-01 | 2026-11-30 | DHP | DHP-D | John Bryan C. Payongayong | 2- Rate nego
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-306 | INST System Supervisor (Process) Tr-9/11 #2 | 2025-03-01 | 2027-06-30 | DHP | DHP-D | John Allan Florino PALLONTES | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-307.1 | PCC INST Supervisor #1 | 2025-04-01 | 2027-06-30 | DHP | DHP-D | Abhilash Joy | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-307.2 | PCC INST Supervisor #2 | 2025-03-01 | 2027-06-30 | DHP | DHP-D | Imran Khan | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-308 | INST Engineer (U&O) Tr-9/11 #1 | 2025-02-15 | 2027-03-15 | DHP | DHP-C | RONNIE MEDINA MALLARI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-31 | Commissioning Lead Supervisor (Process) Tr-8/10 #1 | 2023-06-01 | 2026-12-31 | DHP | DHP-C | Sunilkumar Jadhav | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-310 | INST Lead Supervisor (U&O) Tr-9/11 | 2025-04-01 | 2027-02-28 | DHP | DHP-C | HAzem Shanah Mohammad Malik HERY PURWANTO MOHAMMED MOIN AHMED Pirama | 2- CV under review
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-311 | INST Supervisor (U&O) Tr-9/11 #1 | 2025-04-01 | 2026-11-30 | DHP | DHP-D | Mohammad Shahid Rehaman | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-312 | INST Supervisor (U&O) Tr-9/11 #2 | 2025-06-15 | 2026-12-31 | DHP | DHP-D | Mohammad Nasirullah | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-315 | INST System Lead Engineer (U&O) Tr-9/11 | 2025-04-01 | 2027-02-28 | DHP | DHP-B | Cornel Catalin Abel | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-316 | Senior INST System Engineer (U&O) Tr-9/11 #1 | 2025-03-01 | 2026-07-31 | DHP | DHP-B | Demis Rodi(HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-319 | INST System Engineer (U&O) Tr-9/11 #1 | 2025-07-01 | 2027-05-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-32 | Commissioning Lead Supervisor (Process) Tr-8/10 #2 | 2024-06-01 | 2027-02-28 | DHP | DHP-C | Umesh Anil Naik | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-321 | INST System Supervisor (U&O) Tr-9/11 #1 | 2025-06-01 | 2026-11-30 | DHP | DHP-D | Fasihuz Zama Tojy Kanniakonil (HUB) James(HUB) Clint Dimatatac Alex Anto (Interviewed OK XAvier) | 1- In search
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-323 | Lab Engineer Tr-9/11 => instrumentation Engineer | 2025-04-01 | 2026-01-31 | DHP | DHP-C | KIM Kuk Yeong - from Tortue (C/o Samer) Ashley wilkinson - High rate | 2- Waiting for availability confirmation
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-324 | Lab Supervisor Tr-9/11 #1 | 2027-02-01 | 2027-06-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-327 | MECH Comm. Superintendent Tr-8/9/10/11 | 2023-08-01 | 2026-11-30 | TP | B1 | Antonio POLLINO | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-328 | MECH Comm. Deputy Superintendent Tr-8/9/10/11 | 2024-08-01 | 2027-06-30 | CYD | B1 | Jayan Variattil | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-329 | MECH Lead Engineer (Process) Tr-8/10 | 2024-08-01 | 2027-05-31 | CYD | B1 | Hideharu Hashimoto | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-33 | Commissioning Lead Supervisor (Process) Tr-8/10 #3 | 2024-07-01 | 2026-12-31 | DHP | DHP-C | Sanjay Maruti Gharge | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-330 | MECH Engineer (Process) Tr-8/10 #1 | 2024-07-01 | 2027-05-31 | DHP | DHP-C | Pradeep Maljothi | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-331 | MECH Engineer (Process) Tr-8/10 #2 | 2024-10-01 | 2027-07-31 | CYD | DHP-C | Aldrin De Guzman | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-332 | MECH Lead Supervisor (Process) Tr-8/10 #1 | 2024-12-01 | 2027-06-30 | DHP | DHP-C | K. JAYAPRABU | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-333 | MECH Lead Supervisor (Process) Tr-8/10 #2 | 2024-10-01 | 2027-05-31 | DHP | DHP-C | Rinat GUMAROV | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-334 | MECH Lead Supervisor (Process) Tr-8/10 #3 | 2025-03-01 | 2027-01-31 | DHP | DHP-C | Biji Tharekkattu Thekkethil Alex | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-335 | MECH Lead Supervisor (Process) Tr-8/10 #4 | 2025-01-01 | 2027-05-31 | DHP | DHP-C | Jeyakumar Murugeshan | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-336 | MECH Supervisor (Process) Tr-8/10 #1 | 2025-03-01 | 2027-05-31 | DHP | DHP-D | Evgenii Vladimirovich Barakhaev | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-337 | MECH Supervisor (Process) Tr-8/10 #2 | 2024-10-01 | 2027-05-31 | DHP | DHP-D | Ramana Reddy IDAMAKANTI | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-338 | MECH Supervisor (Process) Tr-8/10 #3 | 2025-01-01 | 2026-12-31 | DHP | DHP-D | Jenish Kathirappully Janardhanan | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-339 | MECH Supervisor (Process) Tr-8/10 #4 | 2025-03-01 | 2026-12-31 | DHP | DHP-D | Sherin Chiraparambil Abdul Majeed | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-34 | Commissioning Lead Supervisor (Process) Tr-8/10 #4 | 2024-01-15 | 2027-01-31 | DHP | DHP-C | Mohammad Shamshad Alam | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-340 | MECH Lead Engineer (U&O) Tr-8/10#1 | 2025-12-01 | 2027-02-28 | TP | B1 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-341.1 | MECH Engineer Lead Supervisor (U&O) Tr-8/10 #1 | 2024-11-01 | 2027-01-31 | DHP | DHP-C | Russell Gomez Semira | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-341.2 | MECH Lead Engineer (U&O) Tr-8/10#2 | 2024-07-01 | 2027-06-30 | DHP | DHP-B | Raguvaran Shanmugavelsamy | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-342 | MECH Engineer (U&O) Tr-8/10 #2 | 2024-08-01 | 2027-01-31 | DHP | DHP-C | Mohammadsohel Giteli | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-343 | MECH Engineer (U&O) Tr-8/10 #1 | 2024-07-01 | 2027-02-28 | DHP | DHP-C | Navinkumar Sukhraj PAL (HUB) | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-344 | MECH Lead Supervisor (U&O) Tr-8/10 #2 | 2024-09-01 | 2027-02-28 | DHP | DHP-C | Sathesh Thangathurai | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-345.1 | Mech Lead Supervisor | 2025-04-01 | 2026-12-31 | DHP | DHP-C | Gaurav Rana | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-345.2 | Mech Supervisor 1 | 2025-06-01 | 2027-02-28 | DHP | DHP-D | Kingsley Antony Bhasker | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-345.3 | Mech Supervisor 2 | 2025-04-01 | 2026-12-31 | DHP | DHP-D | SARAVANAN IYYAPPAN | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-347 | MECH Supervisor (U&O) Tr-8/10 #1 | 2025-05-15 | 2027-03-14 | DHP | DHP-D | Rassul Kdyrgaliyev | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-348 | MECH Supervisor (U&O) Tr-8/10 #2 | 2024-08-01 | 2027-01-31 | DHP | DHP-D | Jothimurugan Singaravel | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-349 | MECH Supervisor (U&O) Tr-8/10 #3 | 2024-10-01 | 2027-02-28 | DHP | DHP-D | Aravinthan THATHAIYA | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-35 | Commissioning Lead Supervisor (Process) Tr-8/10 #5 | 2024-10-01 | 2027-01-31 | DHP | DHP-C | Nino Villalobos SALCEDO | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-350 | MECH Supervisor (U&O) Tr-8/10 #4 | 2024-11-01 | 2025-05-19 | DHP | DHP-D | Mahmoud Majed Mahmoud Roushdy | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-350 | MECH Supervisor (U&O) Tr-8/10 #4 | 2025-05-01 | 2027-04-30 | DHP | DHP-D | Karthikeyan Rajamurugan Aatish | 2- CV under review
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-351 | MECH Supervisor (U&O) Tr-8/10 #5 | 2024-09-01 | 2026-01-31 | DHP | DHP-D | Rajeev Raveendran Nair | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-352 | MECH Comm. Lead Engineer #1 Tr-9/11 | 2025-06-10 | 2025-07-25 | CYD | B1 | Takashi Okano | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-352 | MECH Comm. Lead Engineer #1 Tr-9/11 | 2025-06-01 | 2027-06-30 | CYD | B1 | Kotaru Takeshima? | 3- Waiting for PAF/PAAF signed
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-353 | MECH Comm. Lead Engineer Tr-9/11 - 2 | 2025-05-11 | 2027-04-30 | DHP | DHP-B | Adiputra Nugraha | 4- MS2 - Collect of documents
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-354 | MECH Lead Engineer (Process) Tr-9/11 | 2025-03-01 | 2027-06-30 | CYD | B2 | TBN / Potential NFE internal transfer | 2- Waiting for cost approval
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-355 | MECH Engineer (Process) Tr-9/11 #1 | 2025-03-01 | 2027-05-31 | DHP | DHP-C | Jatmico Luhung Kretarto | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-356 | MECH Engineer (Process) Tr-9/11 #2 | 2025-04-01 | 2027-01-31 | DHP | DHP-C | Samil Skaria | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-357 | MECH Lead Supervisor (Process) Tr-9/11 #1 | 2025-04-01 | 2027-01-31 | DHP | DHP-C | Durai Mariappan | 4- MS4 - QVC required
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-358 | MECH Lead Supervisor (Process) Tr-9/11 #2 | 2026-04-01 | 2027-01-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-359 | MECH Lead Supervisor (Process) Tr-9/11 #3 | 2026-01-01 | 2027-01-31 | DHP | DHP-C | Vishak Das Mohandas | 2- Rate nego
NFE - SITE | Process | PCCSU | 14.Commissioning-36 | Commissioning Lead Supervisor (Process) Tr-8/10 #6 | 2024-08-01 | 2027-03-31 | DHP | DHP-C | Mahesh Kumar (Appala Satya U. M. K. Goli) | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-360 | MECH Supervisor (Process) Tr-9/11 #1 | 2026-03-01 | 2027-01-31 | DHP | DHP-D | Ratish Kurup | 2- Waiting for cost approval
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-361 | MECH Supervisor (Process) Tr-9/11 #2 | 2025-06-01 | 2026-05-31 | DHP | DHP-D | SAjeer VALLIYADAN CHATHOTH | 4- MS2 - Waiting for Local contract
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-362 | MECH Supervisor (Process) Tr-9/11 #3 | 2025-06-01 | 2026-08-31 | DHP | DHP-D | Anurudh Rajasekhar | 4- MS2 - Waiting for Local contract
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-364 | MECH Lead Engineer (U&O) Tr-9/11 | 2025-04-01 | 2027-05-31 | DHP | DHP-B | Zakar Sharoon(HUB) | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-365 | MECH Engineer (U&O) Tr-9/11 #1 | 2025-01-01 | 2026-11-30 | DHP | DHP-C | Hernando Aguilar Hernandez | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-367 | MECH Lead Supervisor (U&O) Tr-9/11 #1 | 2025-03-01 | 2027-07-31 | DHP | DHP-C | Dennis Jacob | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-369 | MECH Supervisor (U&O) Tr-9/11 #1 | 2025-08-01 | 2027-07-31 | DHP | DHP-D | Akhlaque AHMAD ? | 3- Waiting for PAF/PAAF issuance
NFE - SITE | Process | PCCSU | 14.Commissioning-37 | Commissioning Lead Supervisor (Process) Tr-8/10 #1 | 2023-09-01 | 2027-06-30 | DHP | DHP-D | Mahendra Dhondiram Jadhav | 5- Mobilized
NFE - SITE | Mechanical | PCCSU | 14.Commissioning-370 | MECH Supervisor (U&O) Tr-9/11 #2 | 2025-02-01 | 2026-09-30 | DHP | DHP-D | Almas Tkatov | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-372 | O&M Manager - Tr-8 | 2024-11-01 | 2026-06-30 | TP | A | Rehan AFTAB -HUB/TPFQ | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-372 | O&M Lead - Tr-10 | 2026-07-01 | 2027-03-31 | TP | B2 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | O&M | PCCSU | 14.Commissioning-373 | Lead Operation Engineer #1 Tr-8/9/10/11 (ON SHIFT) | 2024-07-01 | 2027-05-31 | DHP | DHP-B | Syed Sharique Babar | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-374 | Lead Operation Engineer Tr-8/9/10/11 #2 1 (ON SHIFT) | 2024-04-01 | 2026-12-31 | DHP | DHP-B | Syed Rehan AHMED | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-375 | Operation Engineer Tr-8/9/10/11 #2 (day) | 2024-04-22 | 2026-12-22 | TP | B2 | Georges NASSAR - TEN POC | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-379 | Lead Maintenance Engineer #1 Tr-8/9/10/11 | 2024-03-01 | 2026-09-30 | DHP | DHP-B | Orkhan Milhajov (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-444 | Commissioning Supervisor- Utilities | 2024-12-01 | 2026-09-30 | DHP | DHP-D | MOHD FADLILAH BIN MOHD | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-380 | Maintenance Engineer Tr-8/9/10/11 | 2025-01-01 | 2027-01-31 | DHP | DHP-C | Joy Chirayath Thomas | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-388 | Lead Operation Engineer #3 2 Tr-8/9/10/11 (ON SHIFT) | 2024-11-01 | 2026-05-31 | DHP | DHP-B | Rami Majed Adnan Mohamed ALHAFNAWI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-445 | Commissioning Supervisor- Utilities | 2024-12-01 | 2026-09-30 | DHP | DHP-D | Gadhvi Nashrambhai Bhikhbhai | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-393 | Lead Maintenance Engineer #2 Tr-8/9/10/11 => Maintenance engineer #2 Tr-8/9/10/11 | 2025-01-01 | 2027-02-28 | DHP | DHP-C | Bineesh Valliyankal Thankappan | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-4 | Commissioning Clerk #1 | 2023-11-01 | 2027-07-31 | DHP | DHP-F | Lovely Rimando | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-446 | Commissioning Supervisor- Utilities | 2024-12-01 | 2026-09-30 | DHP | DHP-D | LINGARAJAN Murugan | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-402.1 | ELE Lead Supervisor (U&O) Tr-8/10 | 2024-12-01 | 2026-10-31 | DHP | DHP-C | Sivalingam Vellaiyan | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-402.2 | ELE Lead Supervisor (U&O) Tr-8/10 | 2024-10-01 | 2026-08-31 | DHP | DHP-C | Ronald Jasareno Alto | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-403 | ELE Lead Supervisor Engineer (U&O) Tr-8/10 #5 | 2024-06-01 | 2026-11-30 | DHP | DHP-C | Akram Hussain | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-404 | ELE Supervisor (U&O) Tr-8/10 #9 | 2025-01-01 | 2026-08-31 | DHP | DHP-D | Marimuthu Ravi | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-405 | ELE Supervisor (U&O) Tr-8/10 #10 | 2024-08-01 | 2026-08-31 | DHP | DHP-D | Sebastian George | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-406 | PMX PCC engineer | 2023-07-01 | 2025-10-31 | DHP | DHP-C | Oska de Chandra | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-407 | PC & C LOTO Superintendent -1 | 2025-06-01 | 2027-06-30 | DHP | DHP-B | Jimmy Veluthedathukattil JOSEPH | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-408 | SIMOPS Superintendent - Utilities | 2023-12-12 | 2027-02-28 | DHP | DHP-B | Jesudas Peter IPE | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-409 | Cybersecurity Lead Engineer | 2024-03-01 | 2027-05-31 | DHP | DHP-B | Crispin Magsino DIOMAMPO | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-121 | Commissioning Supervisor (Offsites) (Utilities)#2 (U&O) Tr-8/10 #8 | 2024-12-01 | 2026-03-31 | DHP | DHP-D | Charles Tua Gerton | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-410 | Cybersecurity Senior Supervisor | 2024-06-01 | 2027-02-28 | DHP | DHP-C | Anandarajan Thothan Elanchezhian | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-411 | Cybersecurity Technician | 2024-05-15 | 2027-02-14 | DHP | DHP-D | SHEIK MOHIDEEN JAFFERULLA | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-412 | Cybersecurity Technician | 2024-09-01 | 2027-01-31 | DHP | DHP-D | Allain Patrick Guzman CURA | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-413 | PCC Manager | 2024-06-22 | 2027-06-21 | TP | A | Nasir AFTAB - HUB/TPFQ | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-414 1.PMT-35 | Deputy Commissioning Manager | 2023-06-23 | 2027-06-30 | CYD | A | Akihito SAGAWA | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-415 1.PMT-36 | Completion & Turnover Manager | 2024-12-16 | 2027-04-30 | CYD | A | Takao Tsuneki | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-416 | Commissioning Engineer(process) | 2024-05-01 | 2025-11-30 | CYD | DHP-C | Ronand Huelva | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-417 | Telecom PC&C Superintendent (Common for Process/U&O) | 2024-06-01 | 2025-10-31 | DHP | DHP-B | Sayat Ashimbayev(HUB) | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-418 | Telecom PC&C Engineer (Common for Process/U&O)#1 | 2024-10-01 | 2026-01-31 | DHP | DHP-C | Anar Ibrahim Oglu Anar BAGIROV | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-419 | Commissioning Lead Supervisor - Utilities # 2 | 2025-05-15 | 2026-06-15 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-136 | Commissioning Supervisor (inlet) #3 (U&O) Tr-9/11 #1 | 2024-12-01 | 2027-02-28 | DHP | DHP-D | Sanjay Balkrishna Doshi | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-420 | Commissioning Lead Supervisor Utilities # 4 Offsites | 2025-01-01 | 2025-11-30 | DHP | DHP-C | Nikolai Kokoryshkin | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-421 | PMX PCC engineer | 2024-05-01 | 2025-12-31 | DHP | DHP-C | Saddamul Haque | 5- Mobilized
NFE - SITE | O&M | PCCSU | 14.Commissioning-422 | Operation Engineer | 2024-11-02 | 2025-12-31 | TP | C | Kathryn JAITLY - TP UK | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-424 | Commissioning Lead Supervisor (Utilities U&O) Tr 08/10 #10 => commissioning Engineer | 2025-03-01 | 2026-06-30 | TP | DHP-C | Rodrigue MALLE - TPFQ | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-426 | Telecom PCC Lead Supervisor (Common for Process/U/O) -1 | 2024-12-01 | 2027-03-31 | DHP | DHP-C | Nerepparambil Benny Thomas Jose | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-427 | Telecom PCC Lead Supervisor (Common for Process/U/O) -2 | 2024-09-01 | 2025-10-31 | DHP | DHP-C | Kairat Imangaliyev | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-428 | Telecom PCC Supervisor (Common for Process/U/O) -1 | 2025-01-01 | 2025-12-31 | DHP | DHP-D | Anuar Karazhanov | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-429 | Telecom PCC Supervisor (Common for Process/U/O) -2 | 2025-03-01 | 2025-11-30 | DHP | DHP-D | Mohamed Asif | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-448 | Lead Commissioning Supervisor-Utilities | 2025-01-01 | 2026-09-30 | DHP | DHP-C | Binu Jose Kurisummootil Varghese | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-430 | Telecom PCC Supervisor (Common for Process/U/O) -3 | 2025-03-01 | 2026-02-28 | DHP | DHP-D | ANTON MOSHKIN | 5- Mobilized
NFE - SITE | Instrum & CS | PCCSU | 14.Commissioning-431 | Telecom PCC Supervisor (Common for Process/U/O) -4 | 2024-12-01 | 2025-11-30 | DHP | DHP-D | Philipose Kondekerial POULOSE | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-432 | SIMOPS Superintendent - O/I - 3 | 2024-11-10 | 2027-03-09 | DHP | DHP-B | Syed Waseem HUSSAIN | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-433 | SIMOPS Lead Coordinator - 4 | 2025-05-01 | 2027-05-31 | DHP | DHP-C | Marat Akhmedov | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-435 | PC C LOTO Lead Coordinator -2 | 2025-03-20 | 2027-04-20 | DHP | DHP-D | SenthilKumar Sankaravel | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-436 | PC & C SHES Systems Senior Engineer-2 - Process | 2025-07-01 | 2026-06-30 | TP | C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-116 | Commissioning Supervisor Fresh water 2 (U&O) Tr-8/10 #3 | 2025-07-01 | 2026-07-31 | DHP | DHP-D | Segaran Ramkumar | 4- MS2 - Collect of documents
NFE - SITE | Process | PCCSU | 14.Commissioning-44 | Commissioning Supervisor (Process) Tr-8/10 #8 | 2025-01-01 | 2027-06-30 | DHP | DHP-D | Fariz Hafdiansyah | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-451 | LOTO Coord.-Mechanical 2 | 2024-12-01 | 2027-06-30 | DHP | DHP-D | Md Jasim Alam | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-452 | LOTO Coord.-Mechanical 3 | 2024-12-01 | 2026-10-31 | DHP | DHP-D | James Sandagon Yabour | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-453 | LOTO Coord.-E&I -1 | 2024-12-01 | 2027-06-30 | DHP | DHP-D | Ezra Jeyaantony | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-454 | LOTO Coord.-E&I -2 Mechanical | 2024-12-01 | 2026-10-31 | DHP | DHP-D | TBD | 2- CV under review
NFE - SITE | Electrical | PCCSU | 14.Commissioning-455 | LOTO Coord.-E&I -3 | 2024-12-01 | 2026-10-31 | DHP | DHP-D | Mohammad Altaf KHAN | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commisioning-458 | PC & C SHES Systems Engineer-1 - U&O | 2023-10-01 | 2027-06-30 | DHP | DHP-B | Jesus Ruiz COELLO - HUB | 5- Mobilized
NFE - SITE | Support | PCCSU | 14.Commissioning-459 | SIMOPS Manager | 2025-01-01 | 2027-06-30 | DHP | DHP-A | Vasilii Tretiakov | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-46 | Commissioning Supervisor (Process) Tr-8/10 #10 | 2025-01-01 | 2026-11-30 | DHP | DHP-D | CARLITO D. CUETO | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-47 | Commissioning Supervisor (Process) Tr-8/10 #11 | 2025-01-01 | 2026-11-30 | DHP | DHP-D | Ryan Jay Borja Atendido | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-461 | PCCSU Electrical Engineer - Process | 2025-01-01 | 2025-08-31 | DHP | DHP-C | Askar Kurmashov | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-462 | PCCSU Electrical Engineer - UOI | 2025-01-01 | 2025-08-31 | DHP | DHP-C | Syed ALIMUDEEN RAFIUDEEN | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-463 | PCCSU Electrical Engineer - UOI | 2025-01-01 | 2025-08-31 | DHP | DHP-C | Ali Mezaoui | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-464 | PCCSU Electrical Engineer - UOI | 2025-01-01 | 2025-08-31 | DHP | DHP-C | Selvarayar NALLATHAMBI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-447 | Commissioning Supervisor- Utilities | 2025-02-01 | 2026-11-30 | DHP | DHP-D | Arunraj Kuruvanancheri | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-449 | Lead Commissioning Supervisor-Utilities | 2025-02-01 | 2026-10-31 | DHP | DHP-C | Darwin Casalda | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-123 | Commissioning Supervisor -inlet 2 (U&O) Tr-8/10 #10 | 2025-03-01 | 2027-06-30 | DHP | DHP-D | Irfan Khan | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-460 | PCCSU Electrical Engineer - Process => Electrical Commissioning Supervisor | 2025-03-01 | 2026-02-28 | DHP | DHP-D | Kaci Chabane | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-50 | Commissioning Supervisor (Process) Tr-8/10 #14 | 2025-03-01 | 2026-11-30 | DHP | DHP-D | Jose Edgar Abadines VILLAR | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-51 | Commissioning Supervisor (Process) Tr-8/10 #15 | 2025-03-01 | 2026-11-30 | DHP | DHP-D | Orhan Erkul | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-43 | Commissioning Supervisor (Process) Tr-8/10 #7 | 2025-04-01 | 2027-07-31 | DHP | DHP-D | Alan Gunawan | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-45 | Commissioning Supervisor (Process) Tr-8/10 #9 | 2025-06-01 | 2027-07-31 | DHP | DHP-D | AWNISH KUMAR SHUKLA | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-59 | Commissioning Lead Engineer (Process) Tr-9/11 #1 | 2025-04-03 | 2027-07-31 | CYD | B1 | Takaaki MURASE | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-60 | Commissioning Lead Engineer (Process) Tr-9/11 #2 | 2024-11-01 | 2027-05-31 | CYD | B1 | Mihashi MASAKI | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-61 | Commissioning Lead Engineer (Process) Tr-9/11 #3 | 2027-03-01 | 2027-06-30 | CYD | B1 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-62 | Commissioning Engineer (Process) Tr-9/11 #1 | 2025-04-01 | 2027-01-31 | CYD | B2 | Natsuru Yamauchi | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-63 | Commissioning Engineer (Process) Tr-9/11 #2 | 2025-06-01 | 2027-04-30 | CYD | B2 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-64 | Commissioning Engineer (Process) Tr-9/11 #3 | 2025-06-01 | 2027-01-31 | CYD | B2 | T. Okamoto / K. Kurashima | 2- Waiting for availability confirmation
NFE - SITE | Process | PCCSU | 14.Commissioning-65 | Commissioning Engineer (Process) Tr-9/11 #4 | 2025-04-01 | 2027-03-31 | DHP | DHP-C | Eric Sandoval Rosales | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-66 | Commissioning Engineer (Process) Tr-9/11 #5 | 2025-12-01 | 2027-05-31 | DHP | DHP-C | Gamaliel Paul Gonzales | 2- Waiting for cost approval
NFE - SITE | Process | PCCSU | 14.Commissioning-67 | Commissioning Engineer (Process) Tr-9/11 #6 | 2025-05-01 | 2026-12-31 | DHP | DHP-C | Mark Noah Docot Bernaldez | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-68 | Commissioning Lead Supervisor (Process) Tr-9/11 #1 | 2025-07-01 | 2026-09-30 | DHP | DHP-C | BENJAMIN DEL SOCORRO UBAS | 4- MS2 - Collect of documents
NFE - SITE | Process | PCCSU | 14.Commissioning-69 | Commissioning Lead Supervisor (Process) Tr-9/11 #2 | 2025-07-01 | 2026-12-31 | DHP | DHP-C | Fermino Mendoza | 4- MS5 - FT / Site Mob confirmation
NFE - SITE | Management | PCCSU | 14.Commissioning-7 | Commissioning Interface Engineer | 2024-02-01 | 2027-05-31 | DHP | DHP-C | Kiran Kumar Bhaskara Raju (HUB) | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-70 | Commissioning Lead Supervisor (Process) Tr-9/11 #3 | 2026-02-01 | 2027-01-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-71 | Commissioning Lead Supervisor (Process) Tr-9/11 #4 | 2026-02-01 | 2027-01-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-72 | Commissioning Lead Supervisor (Process) Tr-9/11 #5 | 2025-07-01 | 2026-12-31 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-73 | Commissioning Lead Supervisor (Process) Tr-9/11 #6 | 2025-07-01 | 2026-09-30 | DHP | DHP-C | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Material | PCCSU | 14.Commissioning-8 | Commissioning Supporting Team Lead | 2025-06-01 | 2027-03-31 | DHP | DHP-C | Dennis Belen Ofiaza | 5- Mobilized
NFE - SITE | Electrical | PCCSU | 14.Commissioning-195.1 | ELE Lead Supervisor (U&O) Tr-9/11 => Pre-Commissioning & Commissioning junior Engineer (Electrical) =>Commissioning Supervisor Utilities | 2025-07-01 | 2025-11-30 | VIE=>Apprentice | TP-E | Leopold SZEMES | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-83 | Commissioning Supervisor (Process) Tr-9/11 #10 | 2025-07-01 | 2026-12-31 | DHP | DHP-D | Maulana Rizki | 4- MS2 - Collect of documents
NFE - SITE | Process | PCCSU | 14.Commissioning-84 | Commissioning Supervisor (Process) Tr-9/11 #11 | 2025-07-01 | 2026-09-30 | DHP | DHP-D | Jefri Armin Sitorus | 4- MS1 required
NFE - SITE | Process | PCCSU | 14.Commissioning-85 | Commissioning Supervisor (Process) Tr-9/11 #12 | 2025-07-01 | 2026-09-30 | DHP | DHP-D | Herwid Donno | 3- Waiting for PAF/PAAF signed
NFE - SITE | Process | PCCSU | 14.Commissioning-86 | Commissioning Supervisor (Process) Tr-9/11 #13 | 2025-07-01 | 2026-09-30 | DHP | DHP-D | Aravinthkumar Moorthi | 2- Rate nego
NFE - SITE | Process | PCCSU | 14.Commissioning-56 | Commissioning Superintendent (Process) Tr-9/11 #1 | 2025-07-01 | 2026-12-31 | CYD | B1 | Constantin-Florian Toba | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-74 | Commissioning Supervisor (Process) Tr-9/11 #1 | 2025-07-01 | 2026-12-31 | DHP | DHP-D | Azeem Anwar | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-75 | Commissioning Supervisor (Process) Tr-9/11 #2 | 2025-07-01 | 2026-12-31 | DHP | DHP-D | Muhammad Latif | 4- MS1 required
NFE - SITE | Process | PCCSU | 14.Commissioning-76 | Commissioning Supervisor (Process) Tr-9/11 #3 | 2025-07-01 | 2026-09-30 | DHP | DHP-D | VIRGINIO SALVADOR SANTOS | 4- MS3 - Docs submitted for visa application
NFE - SITE | Process | PCCSU | 14.Commissioning-57 | Commissioning Superintendent (Process) Tr-9/11 #2 | 2025-07-01 | 2026-12-31 | CYD | B1 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-58 | Commissioning Superintendent (Process) Tr-9/11 #3 | 2025-08-01 | 2026-12-31 | CYD | B1 | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-77 | Commissioning Supervisor (Process) Tr-9/11 #4 | 2025-07-01 | 2026-09-30 | DHP | DHP-D | Iman Rusmana | 4- MS4 - Waiting for hotel booking/site arrangements
NFE - SITE | Process | PCCSU | 14.Commissioning-78 | Commissioning Supervisor (Process) Tr-9/11 #5 | 2025-12-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-79 | Commissioning Supervisor (Process) Tr-9/11 #6 | 2025-12-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-87 | Commissioning Supervisor (Process) Tr-9/11 #14 | 2025-08-01 | 2026-09-30 | DHP | DHP-D | Francis Sison | 3- Waiting for PAF/PAAF signed
NFE - SITE | Process | PCCSU | 14.Commissioning-88 | Commissioning Supervisor (Process) Tr-9/11 #15 | 2025-08-01 | 2026-09-30 | DHP | DHP-D | Leo Arockiasamy | 3- Waiting for PAF/PAAF signed
NFE - SITE | Process | PCCSU | 14.Commissioning-80 | Commissioning Supervisor (Process) Tr-9/11 #7 | 2026-01-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-81 | Commissioning Supervisor (Process) Tr-9/11 #8 | 2026-01-01 | 2026-11-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-82 | Commissioning Supervisor (Process) Tr-9/11 #9 | 2025-07-01 | 2026-12-31 | DHP | DHP-D | Roderick Panopio | 2- Rate nego
NFE - SITE | Process | PCCSU | 14.Commissioning-89 | Commissioning Supervisor (Process) Tr-9/11 #16 | 2025-08-01 | 2026-09-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Process | PCCSU | 14.Commissioning-90 | Commissioning Supervisor (Process) Tr-9/11 #17 | 2025-08-01 | 2026-09-30 | DHP | DHP-D | TBN / Potential NFE internal transfer | 1- In search
NFE - SITE | Management | PCCSU | 14.Commissioning-93 | PC&C Utilities Manager | 2023-08-01 | 2027-05-31 | TP | B1 | Vincent JACQUENOT | 5- Mobilized
NFE - SITE | Management | PCCSU | 14.Commissioning-95 | PC&C Inlet Manager | 2023-08-01 | 2026-11-30 | TP | B1 | Rafael DOMINGUEZ | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-96 | Commissioning Lead Engineer (U&O) Tr-8/10 #1 =>Commissioning Lead Engineer (Offsites) #1 | 2024-08-01 | 2026-10-31 | DHP | DHP-C | Alibek KAMALOV | 5- Mobilized
NFE - SITE | Process | PCCSU | 14.Commissioning-99 | Commissioning Engineer (Offsites) #2 Tr-8/10 #1 | 2024-01-01 | 2027-02-28 | TP | B2 | Olivier GREGOIRE | 5- Mobilized
NFE - SITE | O&M | PCCSU | 5.Training-1 | Senior O&M Training superintendent Staff #1 | 2024-02-15 | 2026-10-15 | DHP | DHP-B | Dmitrii Li - HUB | 5- Mobilized
NFE - SITE | O&M | PCCSU | 5.Training-3 | O&M Training Lead Coordinator Staff #1 | 2024-08-01 | 2027-03-31 | DHP | DHP-C | Sharat Kumar Elayambari (HUB) | 5- Mobilized
NFE - SITE | O&M | PCCSU | 5.Training-4 => 14.Commissioning-423 | O&M Training Staff #2 => Commissioning Lead Supervisor (U&O) Tr 08/10 #6-Utilities =>O&M Training Staff #2 => Shift Operation Engineer | 2025-05-15 | 2026-07-31 | DHP | DHP-C | Somasundaram Hariharan | 5- Mobilized
NFE - SITE | O&M | PCCSU | 5.Training-5 | O&M Training Coordinator -2 | 2024-08-17 | 2026-09-30 | DHP | DHP-D | Mirza Hammad Baig | 5- Mobilized